## Appraisal
| DOW Opportunities | CROSSRAIL STATIONS | [17 empty] | Applicability across all stations | Action for implementation
Principle | Opportunity description | Bond Street |  |  | Farrigdon |  |  | Liverpool Street |  |  | Paddington |  |  | Tottenham Court Road |  |  | Whitechapel
|  | Principle | Class | Status | Principle | Class | Status | Principle | Class | Status | Principle | Class | Status | Principle | Class | Status | Principle | Class | Status
1. Reuse & Recovery | Use excavated waste to build Wallasea Island site or use as embankments on the network | 1 | A | Y/Y | 1 | A | Y/M | [12 empty] | To all (TBC) | Set requirements in all procurement documentation
| Reuse soil spoil, recycled aggregates or stone from demolition | 1 | A | Y/M |  |  |  | 1 | A | Y/M |  |  |  | 1 | A | Y/M |  |  |  |  | Set requirements in specifications and procurement documentation
| Reuse of fill at Pudding Mill Lane (heavily contaminated site) |  |  |  | 1 | A | Y/M | [13 empty] | Carry out survey to assess viability
| Investigate resale of excavation material (high quality) |  |  |  | 1 | A | Y/M | [13 empty] | Investigate and assess options
| Compel contractors to dispose of all waste wood for reuse through centralised scheme | [6 empty] | 1 | A | Y/Y | [10 empty] | Set requirements in rocurement documentation
| Store and return wooden pallets to suppliers as soon as possible to avoid their damage and waste | [6 empty] | 1 | A | Y/Y | [10 empty] | Set requirements in specifications and procurement documentation
| Create a central Crossrail database/market for contractors/central public to buy/sell unwanted materials | [6 empty] | 1 | A | Y/Y | [10 empty] | Set requirements in all procurement documentation
| Recover and reuse aggregates from Thames gravel | [6 empty] | 1 | A | Y/Y | [10 empty] | Set requirements in specifications and procurement documentation
| Avoid contamination of excavated materials by fuels/conditioning agents/segregation of waste streams | [6 empty] | 1 | A | Y/Y | [10 empty] | Segregate waste on site and separate contaminated waste
| Reuse foundation piles ground slabs | [6 empty] | 1 | A | Y/M | [10 empty] | Carry out survey to assess viability
| Reuse of bentonite or alternative support fluid for D/walls | [9 empty] | 1 | A | Y/Y | [7 empty] | Set requirements in specifications and procurement documentation
| Reuse existing iron railings in urban design | [9 empty] | 1 | A | Y/Y | [7 empty] | Investigate and assess options
| Recover demolition waste from Eastbourne Terrace and departures road. | [9 empty] | 1 | A | Y/Y | [7 empty] | Set requirements in all procurement documentation
| Use material from over ground demolition in construction | [12 empty] | 1 | A | Y/M |  |  |  |  | Set requirements in all procurement documentation
| Reuse excavated material on other projects in London | [9 empty] | 1 | A | Y/Y | 1 | A | Y/M |  |  |  |  | Investigate and assess options
| Use cement substitutes (GGBS & PFA) | 1 | A | Y/Y | 1 | A | Y/Y | 1 | A | Y/Y | 1 | A | Y/Y | 1 | A | Y/Y |  |  |  | To all (TBC) | Quantify impact and set requirements in specifications and procurement documentation
| Create a natural roof coverage that connects the interchange area of the existing line and the new Crossrail line. | [15 empty] | 1 | A | Y/Y |  | Incorporate in the design
| Use reclaimed steel sheets for the perforated and non-perforated corten sheeting. | [15 empty] | 1 | A | Y/M |  | Investigate/assess options and incorporate requirements in specifications and procurement documentation
2. Off Site Construction | Use off-site construction for  Pre-formed rise sectors pipework/ducts/containment  Pre- fabricated main services routes and risers  Packaged plant units (e.g. pumps etc)  Pre-fabricated ‘chilled plant’ and modular air handling unit sections | 2 | A | Y/Y | 2 | A | Y/Y | 2 | A | Y/Y |  |  |  | 2 | A | Y/Y |  |  |  | To all (TBC) | Set requirements in specifications and procurement documentation
| Use modular M&E elements (e.g. cassettes painted and fire proofed off site) to allow for flexibility in maintenance / repair and cater for future technical improvements | 2 | A | Y/M | [9 empty] | 2 | A | Done |  |  |  |  | Set requirements in specifications and procurement documentation
| Use platform modular construction | [12 empty] | 2 | A | Y/Y |  |  |  | To all (TBC) | Quantify impact and set requirements in specifications and procurement documentation
| Use architectural components fabricated off-site |  |  |  | 2 | A | Y/Y | [12 empty] | To all (TBC) | Set requirements in specifications and procurement documentation
| Build pedestrian station bridge in sections off-site and then transport to site for installation only | [15 empty] | 2 | A | Y/Y |  | Set requirements in specifications and procurement documentation
| Prefabricate all concourse units and build using support from existing retaining walls | [15 empty] | 2 | A | Y/Y |  | Investigate and assess options
| Use off-site fabrication of steel structure modules wherever possible | [15 empty] | 2 | A | Y/Y |  | Set requirements in specifications and procurement documentation
| Use off-site fabrication for roof curvature to eliminate off-cuts on site | [15 empty] | 2 | A | Y/M |  | Amend design and set requirements in specifications and procurement documentation
3. Materials Optimisation | Standardise grid sizes across all stations to achieve efficiency in architectural components (floors glazing, cladding and roof) | 3 | A | Y/Y | 3 | A | Y/Y | [9 empty] | 3 | A | Y/M |  | Investigate options and amend design
| Use repetitive/standardised structural grid in each station design | 3 | A | Y/M |  |  |  | 3 | A | Y/Y | 3 | A | Y/Y | 3 | A | Y/Y |  |  |  | To all (TBC) | Quantify impact, amend design and set requirements in specifications and procurement documentation
| Optimise/co-ordinate grid for standard materials/componenent sizes | [6 empty] | 3 | A | Y/Y | 3 | A | Y/M | [6 empty] | To all (TBC) | Investigate options and amend design
| Standardise layout and forms (i.e. precast concrete, re-use formwork) | [12 empty] | 3 | A | Y/Y |  |  |  |  | Investigate options and amend design
| Standardise architectural finishes – repeated elements | [18 empty] | To all (TBC) | Investigate options, amend design and set requirements in specifications
| Use standard equipment (not bespoke) | [12 empty] | 3 | A | Done |  |  |  |  | Investigate options and amend design
| Standardise back of house construction and maintenance materials so that off-cuts from one site can be used on another | 3 | A | Y/Y |  |  |  | 3 | A | Y/Y | 3 | A | Y/Y |  |  |  | 3 | A | Y/Y | To all (TBC) | Quantify impact, amend design and set requirements in specifications and procurement documentation
| Rationalise room sizes and space proofing to minimise excavation | 3 | A | Y/M | [6 empty] | 3 | A | Y/Y | 3 | A | Done |  |  |  | To all (TBC) | Investigate options and amend design
| Ensure that floor to ceiling heights are consistent to encourage off-site fabrication | [15 empty] | 3 | A | Y/Y |  | Investigate options and amend design
| Use small modules of design to reduce the amount of materials used for replacement processes | 3 | A | Y/M | [16 empty] | Investigate options and amend design
| Use the building’s structure to form concrete ventilation ductwork | 3 | A | Y/M | [15 empty] | To all (TBC) | Quantify impact, amend design and set requirements in specifications and procurement documentation
| Use exposed concrete as finished face to reduce additional lining | 3 | A | Y/M | [6 empty] | 3 | A | Y/Y | [7 empty] | Quantify impact, amend design and set requirements in specifications and procurement documentation
| Reduce rebound from sprayed concrete lining | 3 | A | Y/M | [15 empty] | To all (TBC) | Investigate options and set procurement requirements
| Use flat soffit for RC slabs to reduce formwork and offcuts | 3 | A | Y/M | [16 empty] | Investigate options and amend design
| Specify all surface mounted fittings | [9 empty] | 3 | A | Y/Y | [6 empty] | To all (TBC) | Set requirements in specifications and procurement documentation
| Allow for better transfer of loads from over site development to station | [6 empty] | 3 | A | Y/Y | [9 empty] | To all (TBC) | Investigate options and amend design
| Use appropriate pile types/sizes | [9 empty] | 3 | A | Y/Y | [6 empty] | To all (TBC) | Investigate options and amend design
| Minimise or eliminate use of timber as falseworks | [12 empty] | 3 | A | Y/Y |  |  |  | To all (TBC) | Set requirements in specifications and procurement documentation
| Use open canopy to eliminated the need for ventilation equipment and façade at concourse level | [15 empty] | 3 | A | Y/Y |  | Set requirements in specifications and procurement documentation
| Use staged erection to allow reuse of temporary works | [15 empty] | 3 | A | Y/M |  | Set requirements in procurement documentation
| Screen / segregate materials for reuse to minimise spoil removal | 3 | A | Y/Y | [9 empty] | 3 | A | Y/Y |  |  |  |  | Set requirements in procurement documentation
| Develop a project wide database to procure materials that minimise wastage in their production | [6 empty] | 3 | A | Y/Y | [9 empty] | To all (TBC) | Develop database
4. Waste Efficient Procurement | Reduce material delivery with packaging (specify returnable or reusable packaging) | 4 | A | Y/M |  |  |  | 4 | A | Y/Y |  |  |  | 4 | A | Y/Y |  |  |  | To all (TBC) | Set requirements in specifications and procurement documentation
| Packaging to be re-used to remove materials from site | [6 empty] | 4 | A | Y/M | [9 empty] | To all (TBC) | Set requirements in procurement documentation
| Eliminate plastic wrappers and bubble wrap | [12 empty] | 4 | A | Y/Y |  |  |  | To all (TBC) | Set requirements in specifications and procurement documentation
| Use re-usable containers for delivery | 4 | A | Y/Y | [15 empty] | To all (TBC) | Set requirements in specifications and procurement documentation
| Use take-back schemes for unused materials | 4 | A | Y/Y | [9 empty] | 4 | A | Y/Y |  |  |  | To all (TBC) | Set requirements in specifications and procurement documentation
| Use consolidation centres | 4 | A | Y/M | 4 | A | Done |  |  |  | 4 | A |  | 4 | A | Done |  |  |  | To all (TBC) | Set requirements in procurement documentation
| Manage the storage of materials to minimise damage/spoiling | 4 | A | Y/Y | [15 empty] | To all (TBC) | Set requirements in procurement documentation
| Use just in time delivery | 4 | A | Y/Y | [15 empty] | To all (TBC) | Set requirements in procurement documentation
| Use reusable formwork | 4 | A | Y/M | [15 empty] | To all (TBC) | Set requirements in procurement documentation
| Train staff dealing with storage and handling of materials | 4 | A | Y/Y | [15 empty] | To all (TBC) | Set requirements in procurement documentation
| Link goals to procurement (specify/incentivise/educate) via contractor's KPIs | [6 empty] | 4 | A | Y/Y | [9 empty] | To all (TBC) | Set requirements in procurement documentation
| Maximise / optimise procurement with overhead development or other stations | 4 | A | Y/M | [9 empty] | 4 | A | Y/Y |  |  |  | To all (TBC) | Investigate and assess options
| Standardise equipment to reduce the need of use of components from multiple manufacturers | 4 | A | Y/M | [15 empty] | To all (TBC) | Set requirements in procurement documentation
| Develop a building Log Book to record equipment disassembly information | [12 empty] | 5 | A | Y/Y |  |  |  |  | Set requirements in procurement documentation
| Design for ease of future deconstruction | [12 empty] | 5 | A | Done |  |  |  |  | Investigate and assess options
| Specify long lives of components | 5 | A | Y/M | [16 empty] | Set requirements in specifications and procurement documentation
1 | Use excavated Thames gravel as aggregates | 1 | B
| Substitute virgin materials and reuse materials from demolition | 1 | B
| Use crushed concrete from demolition as backfill/non structural concrete on site | 1 | B |  | 1 | B | Y/M | 1 | B |  |  |  |  | 1 | B |  | 1 | B
| Re-use existing piles |  |  |  | 1 | B
| Design hand rails from recycled materials | [6 empty] | 1 | B
| Develop a Crossrail standard for secondary concrete elements which can be reinforced with reclaimed reinforcing bars | [6 empty] | 1 | B
| Re-use existing Paxton canopy | [9 empty] | 1 | B
| Recycle materials from the demolition of Block C at Macmillan House and Praed Street buildings | [9 empty] | 1 | B
| Reuse retaining wall as foundation for new structure | [15 empty] | 1 | B
2 | Use pre-cast formwork |  |  |  | 2 | B | Y/M
| Use electrical Power Track |  |  |  | 2 | B | Y/M
| Use modular systems of construction for rail track, precast GMC concrete | [15 empty] | 2 | B
| Use precast elements for secondary and non-critical structure within the box | [9 empty] | 2 | B
3 | Challenge factors/standards that are influence the dimensioning of walls and piles | 3 | B |  |  |  |  | 3 | B |  |  |  |  | 3 | B
| Challenge standards – over specification of material |  |  |  | 3 | B | Done
| Use displacement or driven piles | 3 | B
| Reuse demolition waste as aggregate for main construction | 3 | B
| Coordinate the procurement and specifications with the overhead development | 3 | B
| Make storey heights/rooms sizes multiples of block sizes to avoid cutting |  |  |  | 3 | B | Y/M
| Reduce the amount of cable/trunking – HV Cable C164 |  |  |  | 3 | B | Y/M
| Reduce tunnel size / length |  |  |  | 3 | B | Y/M
| Don’t change the design/specification post materials ordering | [6 empty] | 3 | B
| Use blocks for internal walls wherever possible instead of concrete | [9 empty] | 3 | B
| Incorporate ducts and risers within floors and walls | [9 empty] | 3 | B
| Reduce cladding externally around vent towers | [9 empty] | 3 | B
| Modify uplift factors of safety on piling to reduce depth/numbers of piles |  |  |  | 3 | B |  |  |  |  | 3 | B
| Use trial excavations of D/walls leading to better understanding of ground behaviour and reduce need/risk/cost of protection measures | [9 empty] | 3 | B
| Optimise impact of TBM on construction sequence | [9 empty] | 3 | B
| Optimise wall thickness | [9 empty] | 3 | B
| Shared use of site and plants between Crossrail Railway Line and London Underground | [12 empty] | 3 | B
| Build to British Standards rather than London Underground/Crossrail Railway Line standards | [12 empty] | 3 | B
| Standardise materials (where possible) in station and Over Site Development | [12 empty] | 3 | B
| Optimise station and Over Site Development construction | [12 empty] | 3 | B
| Omit/minimise cladding and general wall finishes / use exposed services | [12 empty] | 3 | B
| Use excavated clays for rammed earth retaining walls / green walls | [15 empty] | 3 | B
4 | Phase concrete deliveries |  |  |  | 4 | B | Y/M
| Use wood – glulam so that waste can be recycled | [6 empty] | 4 | B
| Share more with London Underground or running tunnels | [12 empty] | 4 | B
| Change working hours to allow 24/7 to minimise stop end etc. | [12 empty] | 4 | B
| Use a single contract | [12 empty] | 4 | B
| Combine demolition and construction contracts | [12 empty] | 4 | B
| Implement all Value Engineered items as soon as possible | [12 empty] | 4 | B
| Do not build the station |  |  |  | 5 | B
| Use redundant Liverpool Street signage as memorabilia and put it up for auction | [6 empty] | 1 | C
| Use recycled materials for advertising frames | [6 empty] | 1 | C
| Reuse site hoardings between different/subsequent contractors | [12 empty] | 1 | C
| Save and/or refurbish any office equipment from over ground building for construction | [12 empty] | 1 | C
| Use broken tiles etc from fit-out to create artwork in ticket hall and other areas | [12 empty] | 1 | C
| Use recycled aggregates | [12 empty] | 1 | C
| Recover the HCDL canopy for recycling or reuse | [15 empty] | 1 | C
| Reuse HCDL platform structures as much as possible | [15 empty] | 1 | C
| Use reclaimed materials for cladding floors/ceilings | [15 empty] | 1 | C
| Recover Winthrop Street bridge and Durward Street Bridge for reuse/recycling | [15 empty] | 1 | C
| Reuse materials/fill from removed masonry bridges on site | [15 empty] | 1 | C
| Rebuild Durward Street Bridge by using materials from Winthrop Street Bridge | [15 empty] | 1 | C
| Reuse temporary ticket halls during different construction stages | [15 empty] | 1 | C
| Pre-wire lights with plug and socket connectors | [12 empty] | 2 | C
| Minimise use of Bentonite (i.e. diaphragm wall vs. secant piling) | [12 empty] | 2 | C
| Minimise use of suspended soffits through better design | [12 empty] | 2 | C
| Single spray concrete lining plant for LU & CRL works | [12 empty] | 2 | C
| Minimise temporary works that involves concrete to be broken out | [12 empty] | 2 | C
| Use self levelling concrete | [12 empty] | 2 | C
3 | Use ground source heat pumps to provide heating and cooling | 3 | C
| Select materials with less maintenance/replacement (filters, insulation, light fittings) | [6 empty] | 3 | C
| Provide cooling via ground source heat pumps or use thermal mass of concrete to moderate temperature in station to minimise the need of M&E equipment | [9 empty] | 3 | C
| Design out ‘sharp’ junctions/interfaces to omit requirement for additional protection and rails | [9 empty] | 3 | C
| Design for manufacture not manufacture for design | [6 empty] | 3 | C
4 | Procure the works in packages that provide same or similar materials (e.g. piling and SCL works) | [12 empty] | 4 | C
| Use only suppliers with certified environmental management systems | [12 empty] | 4 | C
5. Deconstruction & Flexibility | Make use of the limited shelf-life for architectural finishes – break up and reuse as base materials |  |  |  | 5 | C
5 | Design structural connections for non-destructive deconstruction | 5 | C
1 | Use demolition waste as art installation | 1 | D
| Recover insulation from demolition work | 1 | D
| Reuse non-contaminated railway sleepers for green wall | [15 empty] | 1 | D
2 | Use prefabricated internal walls | 2 | D
| Design standardised/ prefabricated retail outlet pods in station concourse | [6 empty] | 2 | D
| Use offsite fabrication of M&E services (cluster of services for use of site installation) | [9 empty] | 2 | D
3 | Use active floor plates to generate energy | 3 | D
| Identify finishing materials that can be specified as provisional design on drawings to give contractors opportunity to obtain alternatives on the reclaim materials market | [6 empty] | 3 | D
| Use space above box for storage/car parks etc | [9 empty] | 3 | D
| Use glazed elements at roof level/road level to introduce natural light and reduce lighting load. | [9 empty] | 3 | D
| Use hollow central columns to reduce the concrete used | [9 empty] | 3 | D
| Reduce the amount of contaminated soil through ground improvement and separation | [12 empty] | 3 | D
| Reduce the amount of temporary works | [12 empty] | 3 | D
| Change construction method to bottom up to eliminate use/need for blinding concrete for slab construction | [12 empty] | 3 | D
4 | Use existing railway lines in close proximity to haul waste | [6 empty] | 4 | D
| Offer off-cuts for free to public | [12 empty] | 4 | D
| Ensure that site does not impose constraints | [12 empty] | 4 | D
| Introduce incentives on contractors to meet recycling targets | [12 empty] | 4 | D
5 | Dismantle items off site when then need to be replaced | 5 | D

## Key
1 | Reuse and recovery of materials and components
2 | Off site construction/manufacture
3 | Materials optimisation
4 | Waste efficient procurement
5 | Deconstruction and flexibility
|  | A | Easy to implement, high impact on waste reduction
|  | B | Difficult to implement, high impact on waste reduction
|  | C | Easy to implement, low impact on waste reduction
|  | D | Difficult to implement, low impact on waste reduction
|  |  |  | Done | Already implemented in the design
|  |  |  | Y/Y | Implementation on the project agreed in principle
|  |  |  | Y/M | Implementation on the project desirable subject to further investigation