## Traffic Complaints 2012-2017
Enquiry ID | Nature Of Call | Status | Received Date | Area | Category | Issue | Area of Works | Worksite | Station Type
CRL-00-113381 | Valid Complaint | Closed | 2013-11-20 11:03 | Worksite Related | Public Access and Highway | Lorry Controls | Abbey Wood Station |  | NR
CRL-00-119064 | Valid Complaint | Closed | 2014-03-31 12:33 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Abbey Wood Station |  | NR
CRL-00-120689 | Valid Complaint | Closed | 2014-04-07 14:47 | Worksite Related | Public Access and Highway | Lorry Controls | Abbey Wood Station |  | NR
CRL-00-119489 | Valid Complaint | Closed between 8-10 working days | 2014-04-08 16:46 | Worksite Related | Public Access and Highway | Lorry Controls | Abbey Wood Station |  | NR
CRL-00-120424 | Valid Complaint | Closed | 2014-04-11 12:15 | Worksite Related | Public Access and Highway | Lorry Controls | Abbey Wood Station |  | NR
CRL-00-119653 | Valid Complaint | Closed between 0-5 working days | 2014-04-11 15:15 | Worksite Related | Public Access and Highway | Lorry Controls | Abbey Wood Station |  | NR
CRL-00-121774 | Valid Complaint | Closed | 2014-05-16 11:02 | Worksite Related | Public Access and Highway | Lorry Controls | Abbey Wood Station |  | NR
CRL-00-122146 | Valid Complaint | Closed | 2014-06-12 11:24 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Abbey Wood Station |  | NR
CRL-00-122219 | Valid Complaint | Closed between 0-5 working days | 2014-06-13 16:05 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Abbey Wood Station |  | NR
CRL-00-123526 | Valid Complaint | Closed | 2014-06-18 15:34 | Worksite Related | Public Access and Highway | Lorry Controls | Abbey Wood Station |  | NR
CRL-00-124920 | Valid Complaint | Closed between 6-7 working days | 2014-08-05 00:06 | Worksite Related | Public Access and Highway | Lorry Controls | Abbey Wood Station |  | NR
CRL-00-127965 | Valid Complaint | Closed after 10 working days | 2014-10-07 14:46 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Abbey Wood Station |  | NR
CRL-00-133354 | Valid Complaint | Closed between 0-5 working days | 2014-12-02 16:44 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Abbey Wood Station |  | NR
CRL-00-136351 | Valid Complaint | Closed between 8-10 working days | 2015-04-21 09:29 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Abbey Wood Station |  | NR
CRL-00-138622 | Valid Complaint | Closed after 10 working days | 2015-06-04 09:26 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Abbey Wood Station |  | NR
CRL-00-140198 | Valid Complaint | Closed between 0-5 working days | 2015-07-03 17:23 | Worksite Related | Public Access and Highway | Lorry Controls | Abbey Wood Station |  | NR
CRL-00-142902 | Valid Complaint | Closed between 0-5 working days | 2015-08-27 11:40 | Worksite Related | Public Access and Highway | Lorry Controls | Abbey Wood Station |  | NR
CRL-00-148645 | Valid Complaint | Closed after 10 working days | 2015-12-22 15:01 | Worksite Related | Public Access and Highway | Lorry Controls | Abbey Wood Station |  | NR
CRL-00-148998 | Valid Complaint | Closed between 0-5 working days | 2015-12-23 14:59 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Abbey Wood Station |  | NR
CRL-00-149296 | Valid Complaint | Closed between 0-5 working days | 2016-01-12 16:31 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Abbey Wood Station |  | NR
CLR-00-149771 | Valid Complaint | Closed between 0-5 working days | 2016-01-23 09:15 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Abbey Wood Station |  | NR
CRL-00-164649 | Valid Complaint | Closed after 10 working days | 2017-02-05 15:19 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Abbey Wood Station |  | NR
CRL-00-171929 | Valid Complaint | Closed | 2017-08-14 12:36 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Abbey Wood Station |  | NR
CLR-00-045732 | Valid Complaint | Closed | 2012-03-14 15:49 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Bond Street Station | West Ticket Hall - Davies Street | CS
CRL-00-053177 | Valid Complaint | Closed | 2012-09-12 15:24 | Worksite Related | Public Access and Highway | Lorry Controls | Bond Street Station | West Ticket Hall - Davies Street | CS
CRL-00-053770 | Valid Complaint | Closed | 2012-09-26 09:57 | Worksite Related | Public Access and Highway | Lorry Controls | Bond Street Station | West Ticket Hall - Davies Street | CS
CRL-00-125543 | Valid Complaint | Closed between 0-5 working days | 2014-08-15 12:55 | Worksite Related | Public Access and Highway | Lorry Controls | Bond Street Station | West Ticket Hall - Davies Street | CS
CRL-00-126607 | Valid Complaint | Closed between 0-5 working days | 2014-08-19 13:46 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Bond Street Station |  | CS
CRL-00-127784 | Valid Complaint | Closed between 0-5 working days | 2014-10-06 13:43 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Bond Street Station | West Ticket Hall - Davies Street | CS
CRL-00-131067 | Valid Complaint | Closed between 0-5 working days | 2014-12-19 16:57 | Worksite Related | Public Access and Highway | Lorry Controls | Bond Street Station | West Ticket Hall - Davies Street | CS
CRL-00-136198 | Valid Complaint | Closed between 0-5 working days | 2015-04-16 10:58 | Worksite Related | Public Access and Highway | Lorry Controls | Bond Street Station | West Ticket Hall - Davies Street | CS
CRL-00-136185 | Valid Complaint | Closed between 0-5 working days | 2015-04-17 09:40 | Worksite Related | Public Access and Highway | Lorry Controls | Bond Street Station | East Ticket Hall - Hanover Square | CS
CRL-00-143660 | Valid Complaint | Closed between 0-5 working days | 2015-09-12 09:05 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Bond Street Station | West Ticket Hall - Davies Street | CS
CRL-00-144932 | Valid Complaint | Closed after 10 working days | 2015-10-08 00:54 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Bond Street Station | West Ticket Hall - Davies Street | CS
CRL-00-147486 | Valid Complaint | Closed after 10 working days | 2015-11-26 23:38 | Worksite Related | Public Access and Highway | Lorry Controls | Bond Street Station | West Ticket Hall - Davies Street | CS
CRL-00-152999 | Valid Complaint | Closed after 10 working days | 2016-04-01 15:09 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Bond Street Station | East Ticket Hall - Hanover Square | CS
CRL-00-170801 | Valid Complaint | Closed between 0-5 working days | 2017-07-17 22:00 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Bond Street Station | West Ticket Hall - Davies Street | CS
CRL-00-170894 | Valid Complaint | Closed between 0-5 working days | 2017-07-19 20:24 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Bond Street Station | West Ticket Hall - Davies Street | CS
CRL-00-171791 | Valid Complaint | Closed between 8-10 working days | 2017-08-10 12:08 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Bond Street Station | West Ticket Hall - Davies Street | CS
CRL-00-172264 | Valid Complaint | Closed after 10 working days | 2017-08-18 16:48 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Bond Street Station | West Ticket Hall - Davies Street | CS
CRL-00-175437 | Valid Complaint | Closed between 0-5 working days | 2017-11-14 14:04 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Bond Street Station | West Ticket Hall - Davies Street | CS
CRL-00-175817 | Valid Complaint | Closed between 0-5 working days | 2017-11-26 20:54 | Worksite Related | Public Access and Highway | Lorry Controls | Bond Street Station | West Ticket Hall - Davies Street | CS
CRL-00-176000 | Valid Complaint | Closed | 2017-11-30 15:53 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Bond Street Station | West Ticket Hall - Davies Street | CS
CRL-00-176224 | Valid Complaint | Closed | 2017-12-08 07:33 | Worksite Related | Public Access and Highway | Lorry Controls | Bond Street Station | West Ticket Hall - Davies Street | CS
CRL-00-176382 | Valid Complaint | Closed | 2017-12-13 13:11 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Bond Street Station | LU Bond St Ticket Hall | CS
CRL-00-135904 | Valid Complaint | Closed between 0-5 working days | 2015-04-08 12:05 | Worksite Related | Public Access and Highway | Lorry Controls | Brentwood Station |  | NR
CRL-00-148524 | Valid Complaint | Closed after 10 working days | 2015-12-18 17:49 | Worksite Related | Public Access and Highway | Lorry Controls | Brentwood Station |  | NR
CRL-00-158835 | Valid Complaint | Closed after 10 working days | 2016-09-01 11:12 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Burnham Station |  | NR
CRL-00-101634 | Valid Complaint | Closed | 2013-02-21 09:26 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Connaught Tunnel |  | T
CRL-00-105084 | Valid Complaint | Closed | 2013-05-02 17:10 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Connaught Tunnel |  | T
CRL-00-119669 | Valid Complaint | Closed between 0-5 working days | 2014-04-12 09:01 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Connaught Tunnel | Connaught Tunnel East Bound, Connaught Tunnel West Bound | T
CRL-00-128717 | Valid Complaint | Closed between 0-5 working days | 2014-10-25 19:03 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Custom House Station |  | CS
CRL-00-137596 | Valid Complaint | Closed between 0-5 working days | 2015-05-16 16:27 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Custom House Station |  | CS
CRL-00-053636 | Valid Complaint | Closed | 2012-09-24 10:42 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Farringdon Station | West Ticket Hall - Cardinal Tower | CS
CRL-00-105234 | Valid Complaint | Closed | 2013-05-08 09:41 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Farringdon Station | West Ticket Hall - Cardinal Tower | CS
CRL-00-107625 | Valid Complaint | Closed | 2013-07-02 08:48 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Farringdon Station | East Ticket Hall - including Barbican | CS
CRL-00-108615 | Valid Complaint | Closed | 2013-07-24 11:14 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Farringdon Station | West Ticket Hall - Cardinal Tower | CS
CRL-00-113373 | Valid Complaint | Closed | 2013-11-20 09:47 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Farringdon Station |  | CS
CRL-00-113825 | Valid Complaint | Closed | 2013-11-29 12:28 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Farringdon Station | Smithfield Market | CS
CRL-00-116698 | Valid Complaint | Closed between 0-5 working days | 2014-02-11 17:54 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Farringdon Station | West Ticket Hall - Cardinal Tower | CS
CRL-00-118995 | Valid Complaint | Closed between 0-5 working days | 2014-03-28 12:26 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Farringdon Station |  | CS
CRL-00-119305 | Valid Complaint | Closed between 6-7 working days | 2014-04-03 17:44 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Farringdon Station | West Ticket Hall | CS
CRL-00-133257 | Valid Complaint | Closed between 0-5 working days | 2015-02-15 16:03 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Farringdon Station | West Ticket Hall | CS
CRL-00-140232 | Valid Complaint | Closed between 8-10 working days | 2015-07-06 10:53 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Farringdon Station | West Ticket Hall | CS
CRL-00-141772 | Valid Complaint | Closed after 10 working days | 2015-08-04 16:06 | Worksite Related | Public Access and Highway | Lorry Controls | Farringdon Station | West Ticket Hall | CS
CRL-00-142392 | Valid Complaint | Closed between 0-5 working days | 2015-08-14 12:33 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Farringdon Station | East Ticket Hall - including Barbican | CS
CRL-00-143103 | Valid Complaint | Closed between 0-5 working days | 2015-09-02 10:03 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Farringdon Station | East Ticket Hall - including Barbican | CS
CRL-00-143354 | Valid Complaint | Closed between 8-10 working days | 2015-09-07 10:34 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Farringdon Station | East Ticket Hall - including Barbican | CS
CRL-00-143662 | Valid Complaint | Closed between 0-5 working days | 2015-09-12 14:55 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Farringdon Station | West Ticket Hall | CS
CRL-00-144781 | Valid Complaint | Closed after 10 working days | 2015-10-04 06:45 | Worksite Related | Public Access and Highway | Lorry Controls | Farringdon Station | East Ticket Hall - including Barbican | CS
CRL-00-150828 | Valid Complaint | Closed between 0-5 working days | 2016-02-15 11:16 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Farringdon Station | East Ticket Hall - including Barbican | CS
CRL-00-155822 | Valid Complaint | Closed between 8-10 working days | 2016-06-15 12:20 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Farringdon Station | East Ticket Hall - including Barbican | CS
CRL-00-162141 | Valid Complaint | Closed between 0-5 working days | 2016-11-30 22:56 | Worksite Related | Public Access and Highway | Lorry Controls | Farringdon Station | East Ticket Hall - including Barbican | CS
CRL-00-170239 | Valid Complaint | Closed between 8-10 working days | 2017-07-03 16:25 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Farringdon Station | East Ticket Hall - including Barbican | CS
CRL-00-176505 | Valid Complaint | Closed | 2017-12-11 11:35 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Forest Gate Station |  | NR
CRL-00-148929 | Valid Complaint | Closed between 0-5 working days | 2015-12-30 10:32 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Gidea Park Station |  | NR
CRL-00-148943 | Valid Complaint | Closed between 8-10 working days | 2015-12-31 11:04 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Gidea Park Station |  | NR
CRL-00-157544 | Valid Complaint | Closed between 0-5 working days | 2016-07-29 17:06 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Gidea Park Station |  | NR
CRL-00-141603 | Valid Complaint | Closed between 0-5 working days | 2015-07-31 12:12 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Hayes & Harlington Station |  | NR
CRL-00-146786 | Valid Complaint | Closed between 0-5 working days | 2015-11-13 08:57 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Ilford Station |  | Yard
CRL-00-166414 | Valid Complaint | Closed | 2017-03-27 11:49 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Ilford Yard |  | Yard
CRL-00-127621 | Valid Complaint | Closed between 0-5 working days | 2014-10-02 14:30 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Iver Station |  | NR
CRL-00-149749 | Valid Complaint | Closed between 8-10 working days | 2016-01-11 14:14 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Iver Station |  | NR
CRL-00-153289 | Valid Complaint | Closed between 0-5 working days | 2016-04-11 16:16 | Worksite Related | Public Access and Highway | Lorry Controls | Iver Station |  | NR
CRL-00-156310 | Valid Complaint | Closed | 2016-07-01 15:45 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Langley Station |  | NR
CLR-00-045125 | Valid Complaint | Closed | 2012-03-01 10:48 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Liverpool Street Station | Moorgate (worksite 4) - West | CS
CRL-00-053894 | Valid Complaint | Closed | 2012-09-28 11:53 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Liverpool Street Station | Moorgate (worksite 4) - West | CS
CRL-00-100908 | Valid Complaint | Closed | 2013-02-07 10:54 | Worksite Related | Public Access and Highway | Lorry Controls | Liverpool Street Station | Moorgate (worksite 4) - West | CS
CRL-00-119316 | Valid Complaint | Closed after 10 working days | 2014-04-04 09:27 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Liverpool Street Station | Moorgate (worksite 4) - West | CS
CRL-00-124105 | Valid Complaint | Closed between 0-5 working days | 2014-07-17 16:15 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Liverpool Street Station | Liverpool Street Station | CS
CRL-00-125856 | Valid Complaint | Closed between 0-5 working days | 2014-08-21 21:12 | Worksite Related | Public Access and Highway | Lorry Controls | Liverpool Street Station | Moorgate (worksite 4) - West | CS
CRL-00-144713 | Valid Complaint | Closed between 0-5 working days | 2015-10-02 10:32 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Liverpool Street Station | Moorgate (worksite 4) - West | CS
CRL-00-166023 | Valid Complaint | Closed between 0-5 working days | 2017-03-13 14:37 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Manor Park Station |  | NR
CLR-00-042924 | Valid Complaint | Closed | 2012-01-12 09:34 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Paddington Station | Eastbourne Terrace Work Area 3 | CS
CLR-00-043682 | Valid Complaint | Closed | 2012-01-30 16:34 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Paddington Station |  | CS
CRL-00-048894 | Valid Complaint | Closed | 2012-05-28 15:56 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Paddington Station | Eastbourne Terrace Work Area 3 | CS
CRL-00-049975 | Valid Complaint | Closed | 2012-06-28 19:36 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Paddington Station | Eastbourne Terrace Work Area 3 | CS
CRL-00-050036 | Valid Complaint | Closed | 2012-07-02 15:44 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Paddington Station | Eastbourne Terrace Work Area 3 | CS
CRL-00-050724 | Valid Complaint | Closed | 2012-07-12 16:28 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Paddington Station | Eastbourne Terrace Work Area 3 | CS
CRL-00-051976 | Valid Complaint | Closed | 2012-08-10 11:26 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Paddington Station | Eastbourne Terrace Work Area 3 | CS
CRL-00-051991 | Valid Complaint | Closed | 2012-08-13 10:56 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Paddington Station | Eastbourne Terrace Work Area 3 | CS
CRL-00-058259 | Valid Complaint | Closed | 2012-12-05 09:10 | Worksite Related | Public Access and Highway | Lorry Controls | Paddington Station | Eastbourne Terrace Work Area 3 | CS
CRL-00-060404 | Valid Complaint | Closed | 2013-01-12 02:40 | Worksite Related | Public Access and Highway | Lorry Controls | Paddington Station | Eastbourne Terrace Work Area 3 | CS
CRL-00-106806 | Valid Complaint | Closed | 2013-06-12 11:44 | Worksite Related | Public Access and Highway | Lorry Controls | Paddington Station |  | CS
CRL-00-108303 | Valid Complaint | Closed | 2013-07-16 22:42 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Paddington Station | 191-195 Praed Street Work Area 6 | CS
CRL-00-111215 | Valid Complaint | Closed | 2013-09-29 18:23 | Worksite Related | Public Access and Highway | Lorry Controls | Paddington Station | Eastbourne Terrace Work Area 3 | CS
CRL-00-111532 | Valid Complaint | Closed | 2013-10-07 16:55 | Worksite Related | Public Access and Highway | Lorry Controls | Paddington Station |  | CS
CRL-00-111944 | Valid Complaint | Closed | 2013-10-16 15:25 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Paddington Station | Paddington Integrated Project | CS
CRL-00-121738 | Valid Complaint | Closed between 0-5 working days | 2014-06-03 11:42 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Paddington Station | Eastbourne Terrace Work Area 3 | CS
CRL-00-125135 | Valid Complaint | Closed between 0-5 working days | 2014-08-07 17:27 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Paddington Station |  | CS
CRL-00-133361 | Valid Complaint | Closed between 6-7 working days | 2015-02-16 16:53 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Paddington Station | Eastbourne Terrace Work Area 3 | CS
CRL-00-136279 | Valid Complaint | Closed between 0-5 working days | 2015-04-20 09:59 | Worksite Related | Public Access and Highway | Lorry Controls | Paddington Station | Eastbourne Terrace Work Area 3 | CS
CRL-00-148503 | Valid Complaint | Closed | 2015-12-18 14:38 | Worksite Related | Public Access and Highway | Lorry Controls | Paddington Station | 191-195 Praed Street Work Area 6 | CS
CRL-00-148987 | Valid Complaint | Closed | 2016-01-04 14:14 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Paddington Station | Eastbourne Terrace Work Area 3 | CS
CRL-00-150111 | Valid Complaint | Closed between 0-5 working days | 2016-01-29 18:21 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Paddington Station | Eastbourne Terrace Work Area 3 | CS
CRL-00-150280 | Valid Complaint | Closed between 0-5 working days | 2016-02-02 17:09 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Paddington Station | Eastbourne Terrace Work Area 3 | CS
CRL-00-150810 | Valid Complaint | Closed between 0-5 working days | 2016-02-12 18:12 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Paddington Station | Bakerloo Line Link (LU nominated undertaker) | CS
CRL-00-150529 | Valid Complaint | Closed between 0-5 working days | 2016-01-28 14:43 | Worksite Related | Public Access and Highway | Lorry Controls | Romford Station |  | NR
CRL-00-051212 | Valid Complaint | Closed | 2012-07-23 13:54 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | North Woolwich Portal | SSP
CRL-00-051889 | Valid Complaint | Closed | 2012-08-09 08:24 | Worksite Related | Public Access and Highway | Lorry Controls | Shafts, Portals & Depots | Limmo Peninsula Shaft | SSP
CRL-00-055766 | Valid Complaint | Closed | 2012-10-30 10:28 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | Limmo Peninsula Shaft | SSP
CRL-00-056635 | Valid Complaint | Closed | 2012-11-11 14:24 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | North Woolwich Portal | SSP
CRL-00-056636 | Valid Complaint | Closed | 2012-11-12 14:39 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | North Woolwich Portal | SSP
CRL-00-057441 | Valid Complaint | Closed | 2012-11-21 17:49 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | North Woolwich Portal | SSP
CRL-00-058620 | Valid Complaint | Closed | 2012-12-09 11:30 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | North Woolwich Portal | SSP
CRL-00-059105 | Valid Complaint | Closed | 2012-12-17 10:15 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | North Woolwich Portal | SSP
CRL-00-101260 | Valid Complaint | Closed | 2013-02-14 11:33 | Worksite Related | Public Access and Highway | Lorry Controls | Shafts, Portals & Depots | Eleanor Street Shaft | SSP
CRL-00-102441 | Valid Complaint | Closed | 2013-03-12 09:19 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | North Woolwich Portal | SSP
CRL-00-102678 | Valid Complaint | Closed | 2013-03-14 16:52 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | Connaught Tunnel | SSP
CRL-00-102872 | Valid Complaint | Closed | 2013-03-20 10:30 | Worksite Related | Public Access and Highway | Lorry Controls | Shafts, Portals & Depots | North Woolwich Portal | SSP
CRL-00-103337 | Valid Complaint | Closed | 2013-03-27 19:50 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | North Woolwich Portal | SSP
CRL-00-103252 | Valid Complaint | Closed | 2013-03-28 13:02 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | North Woolwich Portal | SSP
CRL-00-103384 | Valid Complaint | Closed | 2013-04-02 16:09 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | North Woolwich Portal | SSP
CRL-00-104042 | Valid Complaint | Closed | 2013-04-16 20:40 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | North Woolwich Portal | SSP
CRL-00-104593 | Valid Complaint | Closed | 2013-04-26 07:32 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | Connaught Tunnel | SSP
CRL-00-104644 | Valid Complaint | Closed | 2013-04-26 16:32 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | North Woolwich Portal | SSP
CRL-00-104905 | Valid Complaint | Closed | 2013-04-30 13:22 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | North Woolwich Portal | SSP
CRL-00-105087 | Valid Complaint | Closed | 2013-05-03 11:24 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | Pudding Mill Lane Portal | SSP
CRL-00-105421 | Valid Complaint | Closed | 2013-05-13 07:20 | Worksite Related | Public Access and Highway | Lorry Controls | Shafts, Portals & Depots | Pudding Mill Lane Portal | SSP
CRL-00-105682 | Valid Complaint | Closed | 2013-05-16 15:41 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | North Woolwich Portal | SSP
CRL-00-106000 | Valid Complaint | Closed | 2013-05-23 06:48 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | Connaught Tunnel, Victoria Dock Portal | SSP
CRL-00-106057 | Valid Complaint | Closed | 2013-05-25 16:12 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | Connaught Tunnel, Victoria Dock Portal | SSP
CRL-00-106490 | Valid Complaint | Closed | 2013-06-05 13:40 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | North Woolwich Portal | SSP
CRL-00-109360 | Valid Complaint | Closed | 2013-08-09 21:13 | Worksite Related | Public Access and Highway | Lorry Controls | Shafts, Portals & Depots | Connaught Tunnel | SSP
CRL-00-109506 | Valid Complaint | Closed | 2013-08-14 08:18 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | Connaught Tunnel | SSP
CRL-00-112618 | Valid Complaint | Closed | 2013-11-04 14:36 | Worksite Related | Public Access and Highway | Lorry Controls | Shafts, Portals & Depots | Victoria Dock Portal | SSP
CRL-00-113175 | Valid Complaint | Closed | 2013-11-15 15:27 | Worksite Related | Public Access and Highway | Lorry Controls | Shafts, Portals & Depots | Eleanor Street Shaft | SSP
CRL-00-115949 | Valid Complaint | Closed | 2014-01-27 09:58 | Worksite Related | Public Access and Highway | Lorry Controls | Shafts, Portals & Depots | Eleanor Street Shaft | SSP
CRL-00-116104 | Valid Complaint | Closed between 0-5 working days | 2014-01-29 16:08 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | Eleanor Street Shaft | SSP
CRL-00-119815 | Valid Complaint | Closed between 0-5 working days | 2014-04-16 11:51 | Worksite Related | Public Access and Highway | Lorry Controls | Shafts, Portals & Depots | Plumstead Portal | SSP
CRL-00-120173 | Valid Complaint | Closed between 0-5 working days | 2014-04-28 13:03 | Worksite Related | Public Access and Highway | Lorry Controls | Shafts, Portals & Depots | Plumstead Portal | SSP
CRL-00-122608 | Valid Complaint | Closed between 0-5 working days | 2014-06-24 06:49 | Worksite Related | Public Access and Highway | Lorry Controls | Shafts, Portals & Depots | Eleanor Street Shaft | SSP
CRL-00-123118 | Valid Complaint | Closed between 0-5 working days | 2014-07-02 07:29 | Worksite Related | Public Access and Highway | Lorry Controls | Shafts, Portals & Depots | Eleanor Street Shaft | SSP
CRL-00-125058 | Valid Complaint | Closed between 0-5 working days | 2014-08-06 14:37 | Worksite Related | Public Access and Highway | Lorry Controls | Shafts, Portals & Depots | Victoria Dock Portal | SSP
CRL-00-125115 | Valid Complaint | Closed between 0-5 working days | 2014-08-07 08:25 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | Victoria Dock Portal | SSP
CRL-00-125392 | Valid Complaint | Closed between 0-5 working days | 2014-08-12 12:16 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | Victoria Dock Portal | SSP
CRL-00-125914 | Valid Complaint | Closed between 0-5 working days | 2014-08-22 23:01 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | North Woolwich Portal | SSP
CRL-00-126727 | Valid Complaint | Closed between 8-10 working days | 2014-09-11 16:38 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | Stepney Green Shaft | SSP
CRL-00-127754 | Valid Complaint | Closed between 0-5 working days | 2014-10-05 08:13 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | North Woolwich Portal | SSP
CRL-00-127723 | Valid Complaint | Closed between 0-5 working days | 2014-10-05 20:06 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | North Woolwich Portal | SSP
CRL-00-127730 | Valid Complaint | Closed between 0-5 working days | 2014-10-06 06:53 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | North Woolwich Portal | SSP
CRL-00-127731 | Valid Complaint | Closed between 0-5 working days | 2014-10-06 06:55 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | North Woolwich Portal | SSP
CRL-00-130411 | Valid Complaint | Closed between 8-10 working days | 2014-12-05 14:31 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | Eleanor Street Shaft | SSP
CRL-00-134245 | Valid Complaint | Closed between 0-5 working days | 2015-03-03 10:27 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | Stepney Green Shaft | SSP
CRL-00-137277 | Valid Complaint | Closed between 8-10 working days | 2015-05-11 16:35 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | North Woolwich Portal | SSP
CRL-00-137982 | Valid Complaint | Closed between 0-5 working days | 2015-05-24 11:56 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | Plumstead Portal | SSP
CRL-00-138189 | Valid Complaint | Closed between 0-5 working days | 2015-05-27 22:09 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | North Woolwich Portal | SSP
CRL-00-140125 | Valid Complaint | Closed between 0-5 working days | 2015-07-03 09:55 | Worksite Related | Public Access and Highway | Lorry Controls | Shafts, Portals & Depots | Eleanor Street Shaft | SSP
CRL-00-172601 | Valid Complaint | Closed between 0-5 working days | 2017-08-24 08:39 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shafts, Portals & Depots | Plumstead Portal | SSP
CRL-00-155454 | Valid Complaint | Closed | 2016-06-01 16:17 | Worksite Related | Public Access and Highway | Lorry Controls | Shenfield Station |  | NR
CRL-00-158262 | Valid Complaint | Closed between 0-5 working days | 2016-08-17 15:34 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shenfield Station |  | NR
CRL-00-161459 | Valid Complaint | Closed after 10 working days | 2016-11-11 15:44 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shenfield Station |  | NR
CRL-00-162755 | Valid Complaint | Closed between 0-5 working days | 2016-12-14 09:55 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shenfield Station |  | NR
CRL-00-165157 | Valid Complaint | Closed between 0-5 working days | 2017-02-18 08:52 | Worksite Related | Public Access and Highway | Lorry Controls | Shenfield Station |  | NR
CLR-00-165148 | Valid Complaint | Closed | 2017-02-19 07:15 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Shenfield Station |  | NR
CRL-00-110576 | Valid Complaint | Closed | 2013-08-20 12:42 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Slough Station |  | NR
CRL-00-138729 | Valid Complaint | Closed between 8-10 working days | 2015-06-05 13:06 | Worksite Related | Public Access and Highway | Lorry Controls | Slough Station |  | NR
CRL-00-153021 | Valid Complaint | Closed between 0-5 working days | 2016-03-29 09:09 | Worksite Related | Public Access and Highway | Lorry Controls | Slough Station |  | NR
CRL-00-048481 | Valid Complaint | Closed | 2012-05-17 09:46 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Tottenham Court Road Station | Western Ticket Hall - Dean Street | CS
CRL-00-052681 | Valid Complaint | Closed | 2012-08-30 10:59 | Worksite Related | Public Access and Highway | Lorry Controls | Tottenham Court Road Station | Newman Street | CS
CRL-00-100291 | Valid Complaint | Closed | 2013-01-26 19:07 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Tottenham Court Road Station | Eastern Ticket Hall (Astoria, LU Nominated Undertaker) | CS
CRL-00-101202 | Valid Complaint | Closed | 2013-02-13 08:14 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Tottenham Court Road Station | Eastern Ticket Hall (Astoria, LU Nominated Undertaker) | CS
CRL-00-113891 | Valid Complaint | Closed | 2013-12-02 08:27 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Tottenham Court Road Station | Eastern Ticket Hall (Astoria, LU Nominated Undertaker) | CS
CRL-00-122449 | Valid Complaint | Closed between 0-5 working days | 2014-06-19 00:02 | Worksite Related | Public Access and Highway | Lorry Controls | Tottenham Court Road Station | Eastern Ticket Hall - Astoria/Goslett Yard | CS
CRL-00-124444 | Valid Complaint | Closed between 0-5 working days | 2014-07-24 16:00 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Tottenham Court Road Station | Eastern Ticket Hall (Charing Cross Rd LU Nominated Undertaker) | CS
CRL-00-135080 | Valid Complaint | Closed between 0-5 working days | 2015-03-21 11:07 | Worksite Related | Public Access and Highway | Lorry Controls | Tottenham Court Road Station | Eastern Ticket Hall (Astoria, LU Nominated Undertaker) | CS
CRL-00-140649 | Valid Complaint | Closed between 0-5 working days | 2015-07-13 19:21 | Worksite Related | Public Access and Highway | Lorry Controls | Tottenham Court Road Station | Eastern Ticket Hall (Astoria, LU Nominated Undertaker) | CS
CRL-00-143811 | Valid Complaint | Closed between 0-5 working days | 2015-09-16 00:45 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Tottenham Court Road Station | Eastern Ticket Hall (Astoria, LU Nominated Undertaker) | CS
CRL-00-148977 | Valid Complaint | Closed after 10 working days | 2016-01-02 11:18 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Tottenham Court Road Station | Eastern Ticket Hall (Charing Cross Rd LU Nominated Undertaker) | CS
CRL-00-154898 | Valid Complaint | Closed after 10 working days | 2016-05-19 14:02 | Worksite Related | Public Access and Highway | Lorry Controls | Tottenham Court Road Station | Eastern Ticket Hall - Astoria/Goslett Yard | CS
CRL-00-155556 | Valid Complaint | Closed between 0-5 working days | 2016-06-07 22:21 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Tottenham Court Road Station | Eastern Ticket Hall (Charing Cross Rd LU Nominated Undertaker) | CS
CRL-00-162814 | Valid Complaint | Closed after 10 working days | 2016-12-19 21:12 | Worksite Related | Public Access and Highway | Lorry Controls | Tottenham Court Road Station | Eastern Ticket Hall (Charing Cross Rd LU Nominated Undertaker) | CS
CLR-00-048100 | Valid Complaint | Closed | 2012-05-08 07:45 | Worksite Related | Public Access and Highway | Lorry Controls | Tunnelling | Drive H - Plumstead Portal to North Woolwich | T
CRL-00-105467 | Valid Complaint | Closed | 2013-05-10 17:31 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Tunnelling | Drive X - Royal Oak Portal to West of Farringdon Station | T
CRL-00-106775 | Valid Complaint | Closed | 2013-06-12 09:06 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Tunnelling | Drive Y - Limmo Peninsular to East of Farringdon Station | T
CRL-00-108199 | Valid Complaint | Closed | 2013-07-15 11:07 | Worksite Related | Public Access and Highway | Lorry Controls | Tunnelling | Drive X - Royal Oak Portal to West of Farringdon Station | T
CRL-00-110990 | Valid Complaint | Closed | 2013-09-25 09:00 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Tunnelling | Drive Z - Pudding Mill Lane Portal to Stepney Green Shaft | T
CRL-00-113518 | Valid Complaint | Closed | 2013-11-26 09:20 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Tunnelling | Drive X - Royal Oak Portal to West of Farringdon Station | T
CRL-00-119034 | Valid Complaint | Closed between 0-5 working days | 2014-03-29 10:38 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Tunnelling |  | T
CRL-00-123796 | Valid Complaint | Closed between 0-5 working days | 2014-07-13 09:50 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Tunnelling | Drive H - Plumstead Portal to North Woolwich | T
CRL-00-128069 | Valid Complaint | Closed between 0-5 working days | 2014-10-13 10:19 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Tunnelling | Drive H - Plumstead Portal to North Woolwich | T
CRL-00-128094 | Valid Complaint | Closed between 0-5 working days | 2014-10-14 06:30 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Tunnelling | Drive H - Plumstead Portal to North Woolwich | T
CRL-00-129843 | Valid Complaint | Closed between 0-5 working days | 2014-11-21 13:29 | Worksite Related | Public Access and Highway | Lorry Controls | Tunnelling | Drive G - Limmo Peninsular Shaft to Victoria Dock Portal | T
CRL-00-120382 | Valid Complaint | Closed | 2014-03-22 14:47 | Worksite Related | Public Access and Highway | Lorry Controls | West Drayton Station |  | NR
CRL-00-121759 | Valid Complaint | Closed | 2014-04-22 11:02 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | West Drayton Station |  | NR
CRL-00-133894 | Valid Complaint | Closed between 8-10 working days | 2015-02-24 12:24 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | West Drayton Station |  | NR
CLR-00-044536 | Valid Complaint | Closed | 2012-02-17 10:12 | Worksite Related | Public Access and Highway | Lorry Controls | Westbourne Park |  | T
CLR-00-044538 | Valid Complaint | Closed | 2012-02-17 11:15 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Westbourne Park |  | T
CLR-00-058692 | Valid Complaint | Closed | 2012-12-11 10:00 | Worksite Related | Public Access and Highway | Lorry Controls | Westbourne Park |  | T
CRL-00-102546 | Valid Complaint | Closed | 2013-03-12 21:36 | Worksite Related | Public Access and Highway | Lorry Controls | Westbourne Park |  | T
CRL-00-106694 | Valid Complaint | Closed | 2013-06-10 02:32 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Westbourne Park |  | T
CRL-00-107869 | Valid Complaint | Closed | 2013-07-06 09:48 | Worksite Related | Public Access and Highway | Lorry Controls | Westbourne Park |  | T
CRL-00-109355 | Valid Complaint | Closed | 2013-08-12 10:01 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Westbourne Park |  | T
CRL-00-133108 | Valid Complaint | Closed between 0-5 working days | 2015-02-11 15:56 | Worksite Related | Public Access and Highway | Lorry Controls | Westbourne Park |  | T
CRL-00-135486 | Valid Complaint | Closed between 0-5 working days | 2015-03-31 06:58 | Worksite Related | Public Access and Highway | Lorry Controls | Westbourne Park |  | Yard
CRL-00-160175 | Valid Complaint | Closed between 0-5 working days | 2016-10-09 15:50 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Westbourne Park |  | NR
CRL-00-047250 | Valid Complaint | Closed | 2012-04-20 09:35 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Whitechapel Station | Cambridge Heath Shaft & Draft Relief Shaft | SSP
CRL-00-050632 | Valid Complaint | Closed | 2012-07-11 08:48 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Whitechapel Station | Durward Street Box & West Stair Box | CS
CRL-00-117402 | Valid Complaint | Closed between 0-5 working days | 2014-02-25 13:48 | Worksite Related | Public Access and Highway | Lorry Controls | Whitechapel Station | Durward Street Box & West Stair Box | CS
CRL-00-117587 | Valid Complaint | Closed between 0-5 working days | 2014-03-01 07:54 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Whitechapel Station | Durward Street Box & West Stair Box | CS
CRL-00-117588 | Valid Complaint | Closed between 0-5 working days | 2014-03-02 05:20 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Whitechapel Station | Durward Street Box & West Stair Box | CS
CRL-00-118367 | Valid Complaint | Closed between 0-5 working days | 2014-03-17 06:35 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Whitechapel Station | Durward Street Box & West Stair Box | CS
CRL-00-118709 | Valid Complaint | Closed | 2014-03-22 13:26 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Whitechapel Station | Durward Street Box & West Stair Box | CS
CRL-00-121805 | Valid Complaint | Closed between 0-5 working days | 2014-06-04 11:15 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Whitechapel Station |  | CS
CRL-00-129623 | Valid Complaint | Closed between 0-5 working days | 2014-11-17 09:20 | Worksite Related | Public Access and Highway | Lorry Controls | Whitechapel Station | Durward Street Box & West Stair Box | CS
CRL-00-135901 | Valid Complaint | Closed between 0-5 working days | 2015-04-10 10:57 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Whitechapel Station | Durward Street Box & West Stair Box | CS
CRL-00-139326 | Valid Complaint | Closed between 0-5 working days | 2015-06-17 11:00 | Worksite Related | Public Access and Highway | Lorry Controls | Whitechapel Station | Durward Street Box & West Stair Box | CS
CRL-00-141640 | Valid Complaint | Closed between 0-5 working days | 2015-07-31 16:18 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Whitechapel Station | Durward Street Box & West Stair Box | CS
CRL-00-142163 | Valid Complaint | Closed after 10 working days | 2015-08-11 19:30 | Worksite Related | Public Access and Highway | Lorry Controls | Whitechapel Station | Cambridge Heath Shaft & Draft Relief Shaft | CS
CRL-00-144046 | Valid Complaint | Closed between 0-5 working days | 2015-09-19 12:40 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Whitechapel Station |  | T
CRL-00-144214 | Valid Complaint | Closed between 0-5 working days | 2015-09-22 17:22 | Worksite Related | Public Access and Highway | Lorry Controls | Whitechapel Station | Durward Street Box & West Stair Box | CS
CRL-00-144811 | Valid Complaint | Closed after 10 working days | 2015-10-04 21:26 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Whitechapel Station | Durward Street Box & West Stair Box | CS
CRL-00-145167 | Valid Complaint | Closed between 8-10 working days | 2015-10-12 12:10 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Whitechapel Station | Durward Street Box & West Stair Box | CS
CRL-00-145730 | Valid Complaint | Closed between 0-5 working days | 2015-10-23 07:53 | Worksite Related | Public Access and Highway | Lorry Controls | Whitechapel Station | Durward Street Box & West Stair Box | CS
CRL-00-147232 | Valid Complaint | Closed between 0-5 working days | 2015-11-23 17:04 | Worksite Related | Public Access and Highway | Lorry Controls | Whitechapel Station | Durward Street Box & West Stair Box | CS
CRL-00-149496 | Valid Complaint | Closed after 10 working days | 2016-01-18 08:56 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Whitechapel Station | Durward Street Box & West Stair Box | CS
CRL-00-150945 | Valid Complaint | Closed between 0-5 working days | 2016-02-13 11:32 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Whitechapel Station | Durward Street Box & West Stair Box | CS
CLR-00-151426 | Valid Complaint | Closed between 0-5 working days | 2016-02-25 01:45 | Worksite Related | Public Access and Highway | Lorry Controls | Whitechapel Station | Cambridge Heath Shaft & Draft Relief Shaft | SSP
CRL-00-152231 | Valid Complaint | Closed between 0-5 working days | 2016-03-15 10:48 | Worksite Related | Public Access and Highway | Lorry Controls | Whitechapel Station | Whitechapel Road - ticket hall & roadside | SSP
CRL-00-152704 | Valid Complaint | Closed after 10 working days | 2016-03-23 16:39 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Whitechapel Station |  | CS
CRL-00-153253 | Valid Complaint | Closed after 10 working days | 2016-04-08 20:55 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Whitechapel Station | Durward Street Box & West Stair Box | CS
CRL-00-156924 | Valid Complaint | Closed between 0-5 working days | 2016-07-14 13:39 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Whitechapel Station | Durward Street Box & West Stair Box | CS
CRL-00-159531 | Valid Complaint | Closed between 0-5 working days | 2016-09-19 22:04 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Whitechapel Station | Whitechapel Road - ticket hall & roadside | SSP
CRL-00-160694 | Valid Complaint | Closed between 6-7 working days | 2016-10-21 14:19 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Whitechapel Station | Durward Street Box & West Stair Box | CS
CRL-00-160846 | Valid Complaint | Closed between 0-5 working days | 2016-10-26 08:25 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Whitechapel Station | Durward Street Box & West Stair Box | CS
CRL-00-165527 | Valid Complaint | Closed between 0-5 working days | 2017-02-28 22:37 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Whitechapel Station | Durward Street Box & West Stair Box | CS
CRL-00-165996 | Valid Complaint | Closed between 0-5 working days | 2017-03-11 10:10 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Whitechapel Station | Durward Street Box & West Stair Box | CS
CRL-00-168435 | Valid Complaint | Closed between 0-5 working days | 2017-05-18 17:58 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Whitechapel Station | Durward Street Box & West Stair Box | CS
CRL-00-169957 | Valid Complaint | Closed between 0-5 working days | 2017-06-24 23:40 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Whitechapel Station | Durward Street Box & West Stair Box | CS
CRL-00-169958 | Valid Complaint | Closed between 0-5 working days | 2017-06-25 10:45 | Worksite Related | Public Access and Highway | Traffic Management Plan and Lorry Management Plan | Whitechapel Station | Durward Street Box & West Stair Box | CS
CRL-00-047584 | Valid Complaint | Closed | 2012-04-27 12:43 | Worksite Related | Public Access and Highway | Lorry Controls | Woolwich Station | Station Box - Berkeley Homes | SSP
CRL-00-130034 | Valid Complaint | Closed between 0-5 working days | 2014-11-24 10:20 | Worksite Related | Public Access and Highway | Lorry Controls | Woolwich Station |  | T
CRL-00-054190 | Valid Complaint | Closed | 2012-10-04 14:09 | Worksite Related | Public Access and Highway | Lorry Controls
253