## # 1 CXXX ECP Tracker
Employers Completion Process (ECP) for CXXX Contract Completion | [7 empty] | Date notification issued |  | xx-xx-xxxx
Scope: Delete this note and insert short description of scope of contract or sectional completion.
See contact list on tab #2 for Functional Lead contact details on individual items
See contact list on tab #2 for Functional Lead contact details on individual items
FORM | ITEM NO. | FORM DESCRIPTION | CRL SITE OWNER | FINAL SIGN-OFF BY | EVIDENCE | CONTRACTOR STATUS | ECP TEAM STATUS | COMMENTS / PROGRESS UPDATES (Newer comments on top) | ACTION BY: | Action Date
C1 | ITEM NO. | C1: HEALTH &SAFETY Overall CRL Functional Lead: Head of HSE See tab #2 for details on each item. | CRL SITE OWNER | Form C1 final sign-off by Head of HSE See below for details of individual items. | EVIDENCE | CONTRACTOR STATUS | ECP TEAM STATUS | COMMENTS / PROGRESS UPDATES (Newer comments on top) | ACTION BY: | Action Date
C1 | 001 | Has the Health and Safety File (as defined in the Construction (Design and Management Regulations 2015) been handed over and evaluated by the Area Health and Safety Manager as meeting CRLs requirements and coded 1 by the CRL site team. The requirements include specifically to have the seven H and S File elements of information as defined in the Health and Safety File Template ref. CR-XRL-Z7-ZTM-CR001-50001. These sections are also to be cross referenced as separate documents to the corresponding seven sections of the MDL Structure. Health and Safety File – C05.003. | H&S Generalist (Insert Name) | H&S Generalist (Insert Name) | Insert eB reference numbers for (Code 1) approved relevant Health and Safety file(s). File must be saved on eb on the separate 7 sections and must have a separate cover (8th part) links to each of the sections. (See contacts on tab 2) | Open | Open
C1 | 002 | Has the site and any structure, plant (fixed or portable) or equipment, been left in a safe condition? | H&S Generalist (Insert Name) | H&S Generalist (Insert Name) | Site H&S Advisor to confirm Completed / signed-off at the very end of the project. | Open | Open
C1 | 003 | Is the site and any remaining structure, plant or equipment, left in a secure condition to prevent unauthorised entry, damage or misuse ? | H&S Generalist (Insert Name) | H&S Generalist (Insert Name) | Site H&S Advisor to confirm Completed / signed-off at the very end of the project. | Open | Open
C1 | 004 | Has the CDM Control Point 6 (Works Completion) Certificate been issued (not applicable for sectional completions)? | H&S Generalist (Insert Name) | H&S Generalist (Insert Name) | May not apply to Sectional Completion. Please provide reference number to signed Control Point 6 Cert on eB (Insert eB number) Control Point 5(b) - POST ROGS. Completed / signed-off at the very end of the project. | Open | Open
C1 | 005 | Have the above questions been closed out to the satisfaction of CRL Sector Health & Safety Manager? | Head of HSE | Head of HSE | Head of HSC to sign after C1-001 to C1-004 have all been signed off Final C1 sign-off by Head of HSE | Open | Open
C2 | ITEM NO. | C2: TECHNICAL ASSURANCE Overall CRL Functional Lead: Chris Binns See tab #2 for details on each item. | CRL SITE OWNER | Form C2 Final sign-off by Chief Engineer see below for individulal items | EVIDENCE | CONTRACTOR STATUS | ECP TEAM STATUS | COMMENTS / PROGRESS UPDATES (Newer comments on top) | ACTION BY: | Action Date
C2 | 001 | Design of Permanent Works carried out by the Contractor. Final Design Statement FDS(b) submitted and accepted by CRL ? | Engineering Manager (Insert name) | Enginering Manager (FDS(b)) (Insert name) | Signed off Final Design Statement FDS(b). (Insert eB number). | Open | Open
C2 | 002 | Have all CPFR requirements been accepted by CRL & evidence provided in DOORS? | Supervisor's Rep (PFE) and / or Engineering Manager (Insert name) | Head of Requirements | 1) CPFR Design Verification completed and recorded in DOORS database. 2) CPFR Construction Verification completed and recorded in DOORS database; a. The Final RMCR accepted code 1 without any exclusions/ outstanding issues relating to deviations impacting Safety or Functional Requirements. b. All patchworks closed , NCR addressed c. Related partial scope for interfacing systems Requirements at the element in question are closed and evidence provided d. Integration test Requirements in scenario tests closed – test reports code 1 e. All instructed changes implemented/ scope omissions at design stage included and addressed. | Open | Open
C2 | 003 | Have all design related risks related to the contract on the Project Risk Register been closed out? | Engineering Manager (Insert name) | Enginering Manager (Insert name) | Email confirmation / Sign-off from the relevant Engineering Manager to be provided (insert eB reference - as applicable) | Open | Open
C2 | 004 | Have all applications for Concessions against Baseline Standards been granted and any specified conditions closed? | Supervisor's Rep (PFE) and / or Engineering Manager (Insert name) | Head of Technical Assurance | Provide reference to the Concessions Tracker. Email confirmation / Sign-off from Concessions Administrator. | Open | Open
C2 | 005 | Have all required ESM deliverables been accepted as sufficient to demonstrate ESM compliance? (i.e. has it been demonstrated that the scope of works is capable of operation to control the safety risks to future users (incl. operators & maintainers) to As Low as Reasonably Practicable (ALARP)? | Supervisor's Rep (PFE) and / or Engineering Manager (Insert name) | Head of System Safety | Engineering Safety Management requirements as per Volume 2B Part 32 of the Works Information and/or as ammended by later instructions. (insert eB references - as applicable) | Open | Open
C2 | 006 | Has all the evidence necessary to be assessed for compliance under the Interoperability regulations been submitted to the NoBo and have you obtained an ISV or letter of support for your scope of works? | Supervisor's Rep (PFE) and / or Engineering Manager (Insert name) | Head of System Safety | Interoperability requirements closed out on tracker. Contact Hayat for details. ISV or letter of support from NoBo. (insert eB reference) | Open | Open
C2 | 007 | Has evidence been provided that the constructed Permanent Works comply with the Works Information (incorporating Gate 3 design, the modifications to the design instructed through PMIs post Gate 3 and accepted through the Gate Impact Review Process)? | Supervisor's Rep (PFE) (Insert name) | Supervisor's Rep (PFE) (Insert name) | To be confirmed by the Supervisor's Rep (PFE). All associated Certificates / FDO / FDS / SCCCs etc. are complete and signed off. References to be provided (as applicable). | Open | Open
C2 | 008 | Engineering Manager to confirm that all post Gate 3 changes have been subject to Gate impact Review and where required a Gate Impact Report has been prepared by the designer and accepted by CEG Head of Discipline ? | Supervisor's Rep (PFE) (Insert name) | Enginering Manager (Insert name) | Email confirmation / Sign-off from the relevant Engineering Manager to be provided. Email confirmation by Supervisor's Rep (PFE). Sign off by CRL Engineering Manager. | Open | Open
C2 | 009 | Have all CARs, NCRs FCDs & RFIs been closed out or transferred to the Defects List ? | Supervisor's Rep (PFE) (Insert name) | Supervisor's Rep (PFE) (Insert name) | To be confirmed by the Supervisor's Rep (PFE) and the PTR / EOWL database cross checked by the Completion Manager | Open | Open
C2 | 010 | Have observations recorded on EOWL (CRL and IM observations) related to contract’s scope have been either closed out OR added to the COWL as punchwork items so that they remain a contractual obligation of the contractor? NOTE: List of observations requiring closing prior to certifying NEC contract completion is to be agreed with IMs by Supervisor’s Rep. | Supervisor's Rep (PFE) (Insert name) | Supervisor's Rep (PFE) (Insert name) | To be confirmed by the Supervisor's Rep (PFE) and the PTR / EOWL database cross checked by the Completion Manager | Open | Open
C2 | 011 | Handover Team to confirm their acceptance of the Supervisor’s Rep’s statement above (Observations closure). | Supervisor's Rep (PFE) (Insert name) | Not applicable | To be confirmed by the Supervisor's Rep (PFE) and the PTR / EOWL database cross checked by the Handover Manager Note: Not Applicable - covered under C2-010 above and to be signed-off by SR. | Not Applicable | Not Applicable | N/A - This is covered under C2-010 (Observations) and is to be signed-off by the SR.
C2 | 012 | Has the Supervisors’ Rep received a declaration from the Underground and/or Civil HoD that the Underground, Civils and Structural Verification activities (VAPs) have been completed? Where applicable has the Supervisors Rep received a declaration from additional relevant Discipline HoDs (including Railway Systems) that their verification activities have been completed? | Supervisor's Rep (PFE) and / or Engineering Manager (Insert name) | Sign off by relevant Head of Discipline for Architecture (SSPs) | To be confirmed by the Supervisor's Rep (PFE). Sign-off by the Head of Discipline. Provide ECHR and/or relevant references. Contact the HoD for more details. | Open | Open
C2 | 012 | The Discipline HoDs (including Railway Systems), verifies that based on the evidence presented to them, all the outstanding VAP’s, EOWL’s and associated assurance certification have been completed. | Supervisor's Rep (PFE) and / or Engineering Manager (Insert name) | Sign off by relevant Head of Discipline for MEP (SSPs) - (incl. Fire and Routewide M&E where applicable) | To be confirmed by the Supervisor's Rep (PFE). Sign-off by the Head of Discipline. Provide ECHR and/or relevant references. Contact the HoD for more details. | Open | Open
C2 | 012 | The Discipline HoDs (including Railway Systems), verifies that based on the evidence presented to them, all the outstanding VAP’s, EOWL’s and associated assurance certification have been completed. | Supervisor's Rep (PFE) and / or Engineering Manager (Insert name) | Civils & Structures Sign off by the Chief Engineer | To be confirmed by the Supervisor's Rep (PFE). Sign-off by the Chief Engineer Provide ECHR and/or relevant references. Contact the CEng. for more details. | Open | Open
C2 | 012 | The Discipline HoDs (including Railway Systems), verifies that based on the evidence presented to them, all the outstanding VAP’s, EOWL’s and associated assurance certification have been completed. | Supervisor's Rep (PFE) and / or Engineering Manager (Insert name) | Sign off by the relevant Head of Discipline for C6XX (C620, C631, C644, C650, C660) - C620 and C631 - Head of Signalling & Platform Screen Doors - C644 - Head of OHLE and Traction Power - C650 - Head of Bulk Power - C660 - Head of Communications | To be confirmed by the Supervisor's Rep (PFE). Sign-off by the Head of Discipline. Provide ECHR and/or relevant references. Contact the HoD for more details. | Open | Open
C2 | 012 | The Discipline HoDs (including Railway Systems), verifies that based on the evidence presented to them, all the outstanding VAP’s, EOWL’s and associated assurance certification have been completed. | Supervisor's Rep (PFE) and / or Engineering Manager (Insert name) | Sign off by the relevant Head of Discipline for C610: - Sign off by Head of Track - Sign off by Head of OHLE and Traction Power - Sign off by Head of MEP | To be confirmed by the Supervisor's Rep (PFE). Sign-off by the Head of Discipline. Provide ECHR and/or relevant references. Contact the HoD for more details. | Open | Open
C2 | 012 | The Discipline HoDs (including Railway Systems), verifies that based on the evidence presented to them, all the outstanding VAP’s, EOWL’s and associated assurance certification have been completed. | Supervisor's Rep (PFE) and / or Engineering Manager (Insert name) | Sign off by the relevant Head of Discipline for C695: - Sign off by Head of MEP - Sign off by Head of Track - Sign off by Head of Civils | To be confirmed by the Supervisor's Rep (PFE). Sign-off by the Head of Discipline. Provide ECHR and/or relevant references. Contact the HoD for more details. | Open | Open
C2 | 013 | Have all the Red Line Drawings, describing the as-built asset, been submitted and accepted? | Supervisor's Rep (PFE) (Insert name) | Supervisor's Rep (PFE) (Insert name) | To be confirmed by the Supervisor's Rep (PFE). All SCCCs and/or associated certificates (construction etc.) are accepted / Signed off. Completed Red lines / As Built tracker. References to be provided (as applicable). | Open | Open
C2 | 014 | Has the Designer (FDC for Civils, Contractor’s Designer for D and B) completed a 'Confirmation of Red Line Drawings Certificate’? (Reference: CRL1-XRL-Z-ZFM-CR001-50009). | Supervisor's Rep (PFE) (Insert name) | Engineering Manager (EM) (Insert name) | eB reference to the accepted 'Confirmation of Red Line Drawings Certificate'. Sign off by Engineering Manager . | Open | Open
C2 | 015 | Have all the as-built drawings been accepted at Code 1 for Contractor designed MEPA and Railway Systems? (where applicable) | Supervisor's Rep (PFE) (Insert name) | Supervisor's Rep (PFE) (Insert name) | To be confirmed by the Supervisor's Rep (PFE) | Open | Open
C2 | 016 | Has the Contractor provided acceptable as-built surveys and setting out data i.e. control points (if applicable) ? | Supervisor's Rep (PFE) (Insert name) | Supervisor's Rep (PFE) (Insert name) | To be confirmed by the Supervisor's Rep (PFE) | Open | Open
C2 | 017 | 16. Has the Chief Engineer or their representative approved the Watch and Event Items List (Ref: CRL1- XRL-Z3-ZTM-CR001-50018) produced by the S(PFE) in line with the Watch and Event Items Procedure (Ref:CRL1-XRL-Z3-GPD-CR001-50017? | Supervisor's Rep (PFE) (Insert name) | Chief Engineer or delegate | Approved Watch and Events items list to be provided by Supervisor's Rep. (insert eB ref or statement by Sup. Rep. if there are no Watch and Event Items) Sign off by Chief Engineer or their representative. | Open | Open
C2 | 018 | Have all RAM Documents been updated according to Data Recording and Corrective Action System (DRACAS) Records, or a plan is in place? | Engineering Manager (Insert name) | RAM Engineer or Lead Reliability Engineer | RAM documentation (to be updated by T1) Component RAM Compliance Report (to be updated by CRL to confirm that actions are closed and the Component is compliant after being integrated with other assets) Document references to be provided (as applicable). | Open | Open
C2 | 019 | Have all the DRACAS records been uploaded to the DRACAS Database and have any related actions been closed, or a plan is in place? | Engineering Manager (Insert name) | RAM Engineer or Lead Reliability Engineer | DRACAS Database (on eB) updated RAM Analysis Report Updated RAM Demonstration Case Report Document references to be provided (as applicable). | Open | Open
C2 | 020 | Has the technical content of the final revision of COWL been consulted and confirmed with the Chief Engineer or delegate? | Supervisor's Rep (PFE) (Insert name) | Chief Engineer or delegate | Sign-off by the Chief Engineer / delegate. COWL reference to be provided (Insert the eB number here). | Open | Open
C2 | 021 | Has the Cyber Security Information provided by the Contractor for Element Completion Handover Report (ECHR) been accepted Code 1 by CRL? | Supervisor's Rep (PFE) (Insert name) | Chief Information Security Officer | Cyber Security Information - Code 1 (Insert the eB number here). ECHR reference to be provided. (Insert the eB number here). Confirmation / Sign-off by CISO. | Open | Open
C2 | 022 | Have the necessary Assurance Deliverables been provided to allow sufficient completion of the CRL CARE Register? | Supervisor's Rep (PFE) and / or Engineering Manager (Insert name) | Head of Technical Assurance | Provide reference to CARE report to support the ECP. Email confirmation / Sign-off from Concessions Administrator. All CARE deliverables to be Code 1 (ESJ, Concessions, RIRs, Requirements Management reports, RAM Demo reports, ACs, SCCs, PACs etc.). Refer CRL1-XRL-O7-GUI-CR001-50004. | Open | Open
C3 | ITEM NO. | C3: PLANNING & HERITAGE Overall CRL Functional Lead: TfL Consents & Urban Design Manager See tab #2 for details on each item. | CRL SITE OWNER | Form C3 for final sign-off by TfL Consents and Urban Design Manager see below for individual items | EVIDENCE | CONTRACTOR STATUS | ECP TEAM STATUS | COMMENTS / PROGRESS UPDATES (Newer comments on top) | ACTION BY: | Action Date
C3 | 001 | All permanent Planning and Heritage consents including any relevant Bringing-into-Use consents in place? | Supervisor's Rep (PFE) (Insert name) | (TfL) (see also CRL Land use Planning Team point of contact in tab 2) | All permanent Planning & Heritage consents listed in Contractor’s Planning & Heritage Consents Register. Register in eB accepted Code 1 (insert eB reference) Evidencing that all permanent consents have been identified and approved with evidence in eB C3 Consents - Overall: -- All Consent obtained and Conditions discharged -- Up to date completed consent register in eB -- All consent documentation in eB -- Statement of compliance with all planning consents signed by senior member of the contractor team (project director) in eB. | Open | Open
C3 | 002 | Redline / As-built drawings reviewed to confirm they are consistent with consents? | Supervisor's Rep (PFE) (Insert name) | (TfL) (see also CRL Land use Planning Team point of contact in tab 2) | Written confirmation provided by Contractor’s Project Director that all as-built drawings have been reviewed and are consistent with the approved plans and the all approved plans loaded into eB (Insert eB reference of Contractor's Communication) | Open | Open
C3 | 003 | Planning and Heritage consent conditions which relate to permanent works fully discharged and complied with? | Supervisor's Rep (PFE) (Insert name) | (TfL) (see also CRL Land use Planning Team point of contact in tab 2) | All temporary & permanent Planning & Heritage conditions discharged with evidence in eB. Contractor’s final Planning & Heritage Consents Register in eB accepted Code 1. (Insert eB reference) | Open | Open
C3 | 004 | All Highway consents which may be required either for later contracts or operation transferred to relevant contractor/Crossrail? | Supervisor's Rep (PFE) (Insert name) | (TfL) | A completed traffic consents register evidencing all permanent consents have been identified and obtained. (insert eB reference) | Open | Open
C3 | 005 | All Temporary Highway consents closed out with all traffic management removed and highway reinstated to to Highway Authority satisfaction? | Supervisor's Rep (PFE) (Insert name) | (TfL) | A completed traffic consents register evidencing all consents have been closed out and that all reinstatements have been completed to the reasonable satisfaction of the highway authority. (insert eB reference) | Open | Open
C4 | ITEM NO. | C4: ENVIRONMENT Overall CRL Functional Lead: Head of HSE See tab #2 for details on each item. | CRL SITE OWNER | Form C4 for final sign-off by Head of HSE see below for individual items | EVIDENCE | CONTRACTOR STATUS | ECP TEAM STATUS | COMMENTS / PROGRESS UPDATES (Newer comments on top) | ACTION BY: | Action Date
C4 | 001 | All environmental reporting data received (KPIs, recycled content, dust/air quality, noise, water, objectives and targets, carbon footprint/energy model)? | Site Environmental Adviser (Insert name) | Site Environmental Adviser / Head of HSE | Monthly dust monitoring reports prepared by contractor submitted onto eB. (insert eB reference) Air quality monitoring raw data and associated data on location etc. The raw data can either be provided as access to AirQ Web or raw data spreadsheets Confirm all water data is entered onto Rivo Confirm all energy data is entered onto Rivo. Confirm contractors construction energy model spreadsheet is complete, reviewed and submitted on eB.(insert eB reference) Noise monitoring reports prepared by the contractor are all submitted on eB. (insert eB reference) Quarterly reports on O&Ts prepared by contractor are submitted on eB. Recycled content information submitted on netwaste, reviewed and accepted. Any Section 61 consent applications prepared by the contractor and approvals from the Local Authority to be on eB. | Open | Open
C4 | 002 | Site Waste Management Plan completed and signed off? | Site Environmental Adviser (Insert name) | Site Environmental Adviser / Head of HSE | Up -to -Action Date SWMP report on eB and SmartWaste up-to-Action Date. (insert eB reference) FL will also check Smartwaste and confirm sign off. | Open | Open
C4 | 003 | Survey information handed over (contaminated land, ecology)? | Site Environmental Adviser (Insert name) | Site Environmental Adviser / Head of HSE | Contractors Contaminated Land management Plan is complete and on eB.(insert eB reference) Contractors Contaminated Land Risk Assessment is complete and on eB. (insert eB reference) Confirm contractor ecological survey reports are submitted on eB. (insert eB reference) Confirm whether protected species were identified on the site. If yes, flag for handover. Confirm whether presence of invasive species was identified. If yes, report to be submitted on eB with survey results, any management undertaken and any requirements for ongoing management (insert eB reference) | Open | Open
C4 | 004 | Contaminated land verification report accepted? | Site Environmental Adviser (Insert name) | Site Environmental Adviser / Head of HSE | Verification reports checked by CRL and uploaded onto Eb (insert eB reference) | Open | Open
C4 | 005 | Maintenance regime for site (including landscaping, knotweed management) agreed and signed off? | Site Environmental Adviser (Insert name) | Site Environmental Adviser / Head of HSE | Maintenance Plan showing maintenance regime for landscaped areas to ensure biodiversity is maintained. This should include details of the works that have been undertaken (what was procured, where it was obtained from, how and when it was installed and maintained during the contractors care period) and shall provide a specification for ongoing maintenance. (insert eB reference) | Open | Open
C4 | 006 | All CARs, NCRs, incident investigations closed out? | Site Environmental Adviser (Insert name) | Site Environmental Adviser / Head of HSE | CARs and observations from CRL audits to be closed out,all incident investigation reports on RIVO. | Open | Open
| 007 | Environmental design checklists for works complete? | Site Environmental Adviser (Insert name) | Site Environmental Adviser / Head of HSE | All EDCS to be uploaded onto Eb (insert eB reference) | Open | Open
C4 | 008 | Archaeological archive information received (archaeological works only)? | Site Environmental Adviser (Insert name) | Site Environmental Adviser / Head of HSE | Museum of London or equivalent have received and acceptd all archaeological reports and artifacts where applicable. | Open | Open
C4 | 009 | Have boreholes been decommissioned in accordance with EA guidance or have records of retained boreholes been passed to the landowner where it has been agreed they will be left as permanent monitoring locations? | Site Environmental Adviser (Insert name) | Site Environmental Adviser / Head of HSE | Evidence of decomissioning and reinstatement where applicable. | Open | Open
C4 | 010 | CEEQUAL assessment completed and submitted or BREEAM assessment completed and submitted? | Site Environmental Adviser (Insert name) | Site Environmental Adviser / Head of HSE | CEEQUAL/BREEAM report assessed by an approved assessor and completed for construction work and uploaded onto eB. (insert eB reference) | Open | Open
C4 | 011 | Have post construction actions associated with BREEAM/CEEQUAL been clearly communicated to/documentation been made available to the operator, e.g. requirements for seasonal commissioning, Building User Guide? | Site Environmental Adviser (Insert name) | Site Environmental Adviser / Head of HSE | Building User Guide prepared by contractor, uploaded to eB and reviewed and accepted. (insert eB reference) | Open | Open
C4 | 012 | Environment Agency has confirmed that the works approved under Schedule 17 Part 3 have been completed in accordance with any relevant consent requirements and has confirmed that the consent can be closed out? | Site Environmental Adviser (Insert name) | Site Environmental Adviser / Head of HSE | Copy of contractors environmental consents register (insert eB reference) Letter of acknowledgement from EA that consent/s are closed out (insert eB reference) | Open | Open
C4 | 013 | British Waterways Board (now Canal & River Trust) has confirmed that the works which were approved under Schedule 17 Part5 have been completed in accordance with any relevant consent requirements, and has confirmed that the consent can be closed out? | Site Environmental Adviser (Insert name) | Site Environmental Adviser / Head of HSE | Copy of contractors environmental consents register (insert eB reference) Letter of acknowledgement from Canal and River Trust that consent/s are closed out (insert eB reference) | Open | Open
C4 | 014 | Port of London Authority has confirmed that the works approved under Schedule 17 Part 6 have been completed in accordance with any relevant consent requirements, and has confirmed that the consent can be closed out? | Site Environmental Adviser (Insert name) | Site Environmental Adviser / Head of HSE | Copy of contractors environmental consents register (insert eB reference) Letter of acknowledgement from PLA that consent/s are closed out (insert eB reference) | Open | Open
C4 | 015 | All discharge consents & environmental permits which may be required either for later contracts or operation transferred to relevant contractor/Crossrail? | Site Environmental Adviser (Insert name) | Site Environmental Adviser / Head of HSE | Either: Notification of consent/permit approval from EA/CRT/PLA/MMO (insert eB reference) or copy of contractors environmental consents register which documents status of discharge consent/permit application (insert eB reference) | Open | Open
C5 | ITEM NO. | C5: UNDERTAKINGS & ASSURANCES Overall CRL Functional Lead: See tab #2 for details on each item. | CRL SITE OWNER | Form C5 for final sign-off by CRL Commitment Accountable Manager see below for individual items | EVIDENCE | CONTRACTOR STATUS | ECP TEAM STATUS | COMMENTS / PROGRESS UPDATES (Newer comments on top) | ACTION BY: | Action Date
C5 | 001 | Have all applicable U&As been discharged or handed over in accordance with the accepted Commitments Compliance Plan? | Supervisor's Rep (PFE) (Insert name) | U&A Manager | All U & A's commitments on the commitments trackers discharged. (insert eB reference - as applicable) *** NOTE: For the closure of C5 ECP item(s), the Contract's Action Owner (i.e. the PM or their appointed U&A representative) must agree that all the commitments can be closed against the contract with the Commitment Accountable Manager (CAM) at the regular close out meeting on a Tuesday morning (for meeting slots and/or more details, please contact Rob Carr / EvelynS). | Open | Open
C5 | 002 | Has all commitments compliance evidence uploaded into CDT? | Supervisor's Rep (PFE) (Insert name) | U&A Manager | Envidence of compliance uploaded to the CDT | Open | Open
C6 | ITEM NO. | C6: ESTATES Overall CRL Functional Lead: TfL Property See tab #2 for details on each item. | CRL SITE OWNER | Form C6 final sign-off by TfL Property see below for individual items. | EVIDENCE | CONTRACTOR STATUS | ECP TEAM STATUS | COMMENTS / PROGRESS UPDATES (Newer comments on top) | ACTION BY: | Action Date
C6 | 001 | All site/work areas under the custodianship of the contractor have been handed back to the satisfaction of the receiving party and documented on a handback certificate in accordance with the CRL Estates procedure. | Supervisor's Rep (PFE) (Insert name) | Project Manager (PM) | eB reference to the handback / handover certificate. Confirmation by the Estates department and eB reference to the handback / handover certificate | Open | Open
C7 | ITEM NO. | C7: RAIL INTERFACES Overall CRL Functional Lead: Project Manager or Care & Custody Manager See tab #2 for details on each item. | CRL SITE OWNER | Form C7 for final sign-off by CRL Care and Custody Manager see below for individual items | EVIDENCE | CONTRACTOR STATUS | ECP TEAM STATUS | COMMENTS / PROGRESS UPDATES (Newer comments on top) | ACTION BY: | Action Date
C7 | 001 | Has the Site Rep obtained confirmation that the relevant LU Infrastructure Manager is satisfied that the necessary Assurances have been provided in relation to this contract? | Supervisor's Rep (PFE) (Insert name) | Site Rep dealing with LU interface. (Insert name) | CRL Site Rep dealing with the interface stated aside to seek confirmation from the relevant IM Team member that all Work Package Plans (WPPs) have been completed / fulfilled - as applicable. Email confirmation or relevant evidence to be provided. Confirmation and sign off by the CRL Site Rep dealing with the interface stated aside. | Open | Open
C7 | 001 | Has the Site Rep obtained confirmation that the relevant Network Rail Infrastructure Manager is satisfied that the necessary Assurances have been provided in relation to this contract? | Supervisor's Rep (PFE) (Insert name) | Site Rep dealing with NR interface. (Insert name) | CRL Site Rep dealing with the interface stated aside to seek confirmation from the relevant IM Team member that all Work Package Plans (WPPs) have been completed / fulfilled - as applicable. Email confirmation or relevant evidence to be provided. Confirmation and sign off by the CRL Site Rep dealing with the interface stated aside. | Open | Open
C7 | 001 | Has the Site Rep obtained confirmation that the relevant DLR Infrastructure Manager is satisfied that the necessary Assurances have been provided in relation to this contract? | Supervisor's Rep (PFE) (Insert name) | Site Rep dealing with DLR interface. (Insert name) | CRL Site Rep dealing with the interface stated aside to seek confirmation from the relevant IM Team member that all Work Package Plans (WPPs) have been completed / fulfilled - as applicable. Email confirmation or relevant evidence to be provided. Confirmation and sign off by the CRL Site Rep dealing with the interface stated aside. | Open | Open
C7 | 001 | Has the Site Rep obtained confirmation that the relevant London Overground Infrastructure Manager is satisfied that the necessary Assurances have been provided in relation to this contract? | Supervisor's Rep (PFE) (Insert name) | Site Rep dealing with LO interface. (Insert name) | CRL Site Rep dealing with the interface stated aside to seek confirmation from the relevant IM Team member that all Work Package Plans (WPPs) have been completed / fulfilled - as applicable. Email confirmation or relevant evidence to be provided. Confirmation and sign off by the CRL Site Rep dealing with the interface stated aside. | Open | Open
C7 | 002 | Has the Site Rep obtained confirmation that LU 3rd Party Infrastructure Manager got any issues that would indicate that these works cannot be successfully integrated to deliver the completed railway been either resolved or identified for resolution? | Supervisor's Rep (PFE) (Insert name) | Site Rep dealing with LU interface. (Insert name) | CRL Site Rep dealing with the interface stated aside to seek confirmation from the relevant IM Team member that all Work Package Plans (WPPs) have been completed / fulfilled - as applicable. Email confirmation or relevant evidence to be provided. Confirmation and sign off by the CRL Site Rep dealing with the interface stated aside. | Open | Open
C7 | 002 | Has the Site Rep obtained confirmation that Network Rail 3rd Party Infrastructure Manager got any issues that would indicate that these works cannot be successfully integrated to deliver the completed railway been either resolved or identified for resolution? | Supervisor's Rep (PFE) (Insert name) | Site Rep dealing with NR interface. (Insert name) | CRL Site Rep dealing with the interface stated aside to seek confirmation from the relevant IM Team member that all Work Package Plans (WPPs) have been completed / fulfilled - as applicable. Email confirmation or relevant evidence to be provided. Confirmation and sign off by the CRL Site Rep dealing with the interface stated aside. | Open | Open
C7 | 002 | Has the Site Rep obtained confirmation that DLR 3rd Party Infrastructure Manager got any issues that would indicate that these works cannot be successfully integrated to deliver the completed railway been either resolved or identified for resolution? | Supervisor's Rep (PFE) (Insert name) | Site Rep dealing with DLR interface. (Insert name) | CRL Site Rep dealing with the interface stated aside to seek confirmation from the relevant IM Team member that all Work Package Plans (WPPs) have been completed / fulfilled - as applicable. Email confirmation or relevant evidence to be provided. Confirmation and sign off by the CRL Site Rep dealing with the interface stated aside. | Open | Open
C7 | 002 | Has the Site Rep obtained confirmation that London Overground 3rd Party Infrastructure Manager got any issues that would indicate that these works cannot be successfully integrated to deliver the completed railway been either resolved or identified for resolution? | Supervisor's Rep (PFE) (Insert name) | Site Rep dealing with LO interface. (Insert name) | CRL Site Rep dealing with the interface stated aside to seek confirmation from the relevant IM Team member that all Work Package Plans (WPPs) have been completed / fulfilled - as applicable. Email confirmation or relevant evidence to be provided. Confirmation and sign off by the CRL Site Rep dealing with the interface stated aside. | Open | Open
C8 | ITEM NO. | C8: SYSTEMWIDE | N/A | N/A | N/A | CONTRACTOR STATUS | ECP TEAM STATUS | COMMENTS / PROGRESS UPDATES (Newer comments on top) | ACTION BY: | Action Date
C8 | 1 | Has the Contractor provided records / As Built drawings / Red-line drawings for interfaces with Systemwide and have these documents been through an acceptance review where required? | N/A | N/A | N/A | Not Applicable | Not Applicable | N/A - Please refer the procedure Employer's Completion Process CRL1-XRL-O4-GPD-CR001-50018 Rev 8.0.
C8 | 2 | Has the Contractor provided acceptable as built surveys and setting out data (ie control points) where required? | N/A | N/A | N/A | Not Applicable | Not Applicable | N/A - Please refer the procedure Employer's Completion Process CRL1-XRL-O4-GPD-CR001-50018 Rev 8.0.
C8 | 3 | Has the Contractor provided acceptable Health & Safety Files in cases where that Contractor's civil structure is being taken over by Systemwide for fit-out activities? Files to include records and arrangements of all temporary facilities left in place. | N/A | N/A | N/A | Not Applicable | Not Applicable | N/A - Please refer the procedure Employer's Completion Process CRL1-XRL-O4-GPD-CR001-50018 Rev 8.0.
C9 | ITEM NO. | C9: TECHNICAL INFORMATION Overall CRL Functional Lead: Chief Engineer / Head of Technical Information See tab #2 for details on each item. | CRL SITE OWNER | Form C9 for final sign-off by Chief Engineer and Head of Technical Information see below for individual items | EVIDENCE | CONTRACTOR STATUS | ECP TEAM STATUS | COMMENTS / PROGRESS UPDATES (Newer comments on top) | ACTION BY: | Action Date
C9 | 001 | Is the CMDL complete and Code 1, with all deliverables at either Code 1 or 4? • Code 1 or 4 approved for current revision • DDx (ProjectWise drawings) C rev plus “As Built” suitability status • DWG (non-ProjectWise drawings, identified as As-Built or Red Line required) Code 1 or 4 | Supervisor's Rep (PFE) (Insert name) |  | A final signed (code 1) contract CMDL (provide eB reference) submission (in line with the Works Information Vol. 2B (Civils - part 13.3.1, Systems - part 29.2.3.1). All deliverables to be coded as stated aside. Email confirmation / Sign-off by the Functional Lead. | Open | Open
C9 | 002 | Are there any Obsolete/Cancelled Crossrail deliverables required to be re-instated? If so, have these all been submitted and accepted formally?’ | Supervisor's Rep (PFE) (Insert name) |  | Email confirmation by the SR / Contractor / Functional Lead confirming the Obsolete documents' list. | Open | Open
C9 | 003 | With respect to the WCCC, are the outstanding works / defects, including the outstanding deliverables (if any), listed on the COWL, with unique Punchwork numbers? Is the COWL which is to be listed on the WCCC up to date, accepted and coded Code 1? | Supervisor's Rep (PFE) (Insert name) |  | COWL to be up-to-date, accepted and coded Code 1. (insert eB reference) Each COWL item to have a UNIQUE reference for enabling tracking / closure (of Defects). A Delierable / Document if listed on COWL, must have a Unique reference number as well. Email confirmation / Sign-off by the Functional Lead. | Open | Open
C9 | 004 | Has the Asset Data provided by the Contractor been Accepted by the IM without comments, with all PWKs, NCRs, FCDs and Observation Reports closed out? | Supervisor's Rep (PFE) (Insert name) |  | Contact Colm / Igor for details. Provide document reference(s) - as applicable. | Open | Open
C9 | 005 | Is the As Built 3D Master Model and associated 3D Model Issues Report accepted as code 1? | Supervisor's Rep (PFE) (Insert name) |  | As Built 3D Master Coordination Model should be included on code 1 RIR on eB. (Model Issues report superseded by MAAT tracker – see item 007 below) (Insert eB reference for Code 1 RIR(s) incorporating Master Coordination Model) | Open | Open
C9 | 006 | Are all As Built drawings accepted as code 1? | Supervisor's Rep (PFE) (Insert name) |  | All As Built drawings and 3D models listed on Code 1 RIR (Insert eB reference for Code 1 RIR(s) incorporating Master Coordination Model and all As-built drawings) | Open | Open
C9 | 007 | Is the design in accordance with CRL CAD standards and CAD related requirements within the Works Information? | Supervisor's Rep (PFE) (Insert name) |  | Unless covered by a concession, all CAD data must be assured and MAAT tracker (equivalent of Model Issues Report) should be at 100% as reported by CRL CAD Assurance team to MAAT tracker owner Angela McConville. | Open | Open
C9 | 008 | Have all the O&M Deliverables and Manuals been submitted by the Contractor, accepted by the Supervisor’s Rep (PFE) and are they in compliance with CRL requirements? | Supervisor's Rep (PFE) (Insert name) |  | All O&M Manuals required code 1 on eb listed on submission of CMDL (Insert document references - as applicable) No outstanding PWKs / FCDs regarding Assets data, which may lead to changes in AIMS thus affecting the O&Ms. | Open | Open
C9 | 009 | Is all O&M deliverable information available to enable CRL to add all O&M deliverables to the Operational and Maintenance structure on eB and link them to the O&M manuals? | Supervisor's Rep (PFE) (Insert name) |  | All O&M Manuals required code 1 on eb listed on submission of CMDL (Insert document references - as applicable) No outstanding PWKs / FCDs regarding Assets data, which may lead to changes in AIMS thus affecting the O&Ms. | Open | Open
C10 | ITEM NO. | C10: Third Party Agreements Overall CRL Functional Lead: Agreement Register & Compliance Manager / TBC See tab #2 for details on each item. | CRL SITE OWNER | Form C10 for final sign-off by Lead Agreements and compliance Team see below for individual items | EVIDENCE | CONTRACTOR STATUS | ECP TEAM STATUS | COMMENTS / PROGRESS UPDATES (Newer comments on top) | ACTION BY: | Action Date
C10 | 001 | All Third Party Agreements (TPA) that relate to this Contract have been identified by reference to the Agreements Management System and there are no outstanding duties or obligations which would prevent finalisation of the closure process as it relates to the Contract. | Project Manager (Insert name) | Agreement Register and Compliance Manager | Contact Esme Hobbs for more details. | Open | Open
C10 | 002 | Where TPA obligations have been incorporated into the Contract work scope these have been reviewed and deemed discharged. It is to be noted that the majority of TPA obligations are not discharged via the delivery Contracts and are subject to a separate Agreement Close Out and Handover process. | Project Manager (Insert name) | Agreement Register and Compliance Manager | Contact Esme Hobbs for more details. | Open | Open
C10 | 003 | Any outstanding TPA obligations that are related to the Element or Elements associated with this Contract are being managed outside of ECP and within the Agreement Close Out and Handover process. | Project Manager (Insert name) | Agreement Register and Compliance Manager | Contact Esme Hobbs for more details. | Open | Open
C20 | ITEM NO. | C20: Completion Overall CRL Functional Lead: Completion Manager. See tab #2 for details on each item. | CRL SITE OWNER | Form C20 final sign- off by Completion Manager. See below for individual items. | EVIDENCE | CONTRACTOR STATUS | ECP TEAM STATUS | COMMENTS / PROGRESS UPDATES (Newer comments on top) | ACTION BY: | Action Date
C20 | 001 | Have all CARs, NCRs FCDs & RFIs been properly closed out in the system? | Supervisor's Rep (PFE) (Insert name) | Supervisor's Rep (PFE) (Insert name) | To be confirmed by the Supervisor's Rep (PFE) and the PTR / EOWL database cross checked by the Completion Manager Note: Not Applicable - covered under C2-009 and to be signed-off by SR. | Not Applicable | Not Applicable | N/A - This is covered under C2-0009 and is to be signed-off by the SR.
C20 | 002 | Has the C-ICD document (Construction - Interface Coordination Document) or ‘Handover Plan' been submitted by the Contractor and accepted by CRL? | Supervisor's Rep (PFE) (Insert name) | Supervisor's Rep (PFE) (Insert name) | Reference to accepted C-ICD document or Handover Plan on eB | Open | Open
C20 | 003 | Have all packages been completed and Construction Certificates signed off? | Supervisor's Rep (PFE) (Insert name) | Completion Lead - Stations | Reference to the Whole Contract Construction Certificate or Sectional Contract Construction Certificate + list of accepted packages forming the WCCC or SCCC Confirmation / Sign-off by Certification Manager. | Open | Open
C20 | 004 | Has all work scope removed from the current contract been formally transferred to the follow-on contract? Or alternatively has all work scope removed from the current contract been formally accepted by the end user for instances where there is no follow-on contract? Note: List of items de-scoped and transferred/accepted to be attached as evidence. | Project Manager (Insert name) | Project Manager (Insert name) | List of de-scoped items, PMI reference instructing the work to other Contractor or confirmation of secured budget transfer (in PRISM) (insert document reference - as applicable). | Open | Open
C20 | 005 | Does the Contractor have a Care and Maintenance Plan which has been reviewed by CEG and accepted by the CRL Project Manager? | Project Manager (Insert name) | Project Manager (Insert name) | Confirmation and sign off by the Care and Custody Manager / Project Manager (insert eB reference) | Open | Open
C20 | 006 | Has the CRL Project Manager agreed/clarified all handover matters with the Care and Maintenance Manager? | Project Manager (Insert name) | Project Manager (Insert name) | If Handover (to the IM) is achieved and the approved ECHR report is available, please provide the eB / Document reference for the closure / sign-off. OR If the Contractor is handing over the site to Care & Maintenance Manager (instead of the final IM), the evidence of such Handover is to be provided for the closure / sign-off. Confirmation / sign-off by the Care and Custody Team or the Project Manager. | Open | Open
C20 | 007 | Has provision been made for Supervisor’s cover during the Defects Liability Period ? | Supervisor's Rep (PFE) (Insert name) | Completion Manager | Email from SR or Supervisor confirming the availability of SR / cover during the Defects period. or A confirmation letter by the NEC Supervisor. | Open | Open
C20 | 008 | Have all the interfaces with utility providers been closed out? | Supervisor's Rep (PFE) (Insert name) | Project Manager | Email confirmation and sign off by the Interface Manager plus Supervisor Rep.'s sign-off. | Open | Open
C20 | 009 | Has the contractor delivered all training in accordance with the agreed Training Strategy and Plan? | Project Manager (Insert name) |  | Training Completion Certificate reference. (insert eB references as applicable) • Training Strategy and Plans received on eB accepted as code 1, • Training materials received on eB and accepted as code 1. • All training Sessions delivered • Copies of all training assessments and feedback forms for each session received by CRL Training Team. | Open | Open
C30 | ITEM NO. | C30: Authorisation to Accept WCCC Overall CRL Functional Lead: Completion Manager. See tab #2 for details on each item. | CRL SITE OWNER | Final sign-off by Completion Manager | EVIDENCE | CONTRACTOR STATUS | ECP TEAM STATUS | COMMENTS / PROGRESS UPDATES (Newer comments on top) | ACTION BY: | Action Date
C30 | 1 | I confirm that the Employer’s Completion Process for Contract CXXX has been completed to my satisfaction and the Whole Contract Construction Certificate can be accepted. | N/A | Completion Manager | Signed off C1-C20 forms | Open | Open

## # 2 ECP Contact List (OLD) (hidden)
Contact List for the Employers Completion Process (ECP) for CXXX - SCX Project Sectional / Contract Completion (delete as applicable)
FORM | ITEM NO. | QUESTION | Point of contact | Role | Telephone Number | Email address | Sign off process notes.
C1 | ITEM NO. | C1: HEALTH &SAFETY | Steve Mullins | Head of Health and Safety Assurance | 07702 109 969 | SteveMullins@crossrail.tfl.gov.uk | Once all H&S files have been reviewed and accepted as Code 1 and the site inspection has determined that it has been left or handed over as safe and secure, the H&S Site Advisor signs items 1-3. CDM point 6 cert required for 4. Area Manager signs once complete. Form countersigned by Head of H&S Assurance.
C1 | 1 | Has the Health and Safety File (as defined in the Construction (Design and Management Regulations 2015) been handed over and evaluated by the Area Health and Safety Manager as meeting CRLs requirements and coded 1 by the CRL site team. The requirements include specifically to have the seven H and S File elements of information as defined in the Health and Safety File Template ref. CR-XRL-Z7-ZTM-CR001-50001. These sections are also to be cross referenced as separate documents to the corresponding seven sections of the MDL Structure. Health and Safety File – C05.003. | (Insert Name) | Site H&S Advisor |  |  | Site H&S advisor to initial. Final sign off by H&S Head of Assurance (Steve Mullins)
|  |  | Mike Davies | CDM Integrator | 0203 054 4162 (Internal: 84162) | MikeDavies@crossrail.tfl.gov.uk | Mike can provide guidance on the make up of the H+S file. Can be included as a reviewer prior to approval to avoid two reviews one from site and one from H&S Assurance. Mike can also provide Guidance on other CDM requirements if necessary. ( Point 6 Cert)
C1 | 002 | Has the site and any structure, plant (fixed or portable) or equipment, been left in a safe condition? | (Insert Name) | Site H&S Advisor |  |  | Site H&S advisor to initial. Final sign off by H&S Head of Assurance (Steve Mullins)
C1 | 003 | Is the site and any remaining structure, plant or equipment, left in a secure condition to prevent unauthorised entry, damage or misuse ? | (Insert Name) | Site H&S Advisor |  |  | Site H&S advisor to initial. Final sign off by H&S Head of Assurance (Steve Mullins)
C1 | 004 | Has the CDM Control Point 6 (Works Completion) Certificate been issued (not applicable for sectional completions)? | (Insert Name) | Site H&S Advisor |  |  | Site H&S advisor to initial. Final sign off by H&S Head of Assurance (Steve Mullins)
C1 | 005 | Have the above questions been closed out to the satisfaction of CRL Sector Health & Safety Manager? | (Insert Name) | Area H&S Manager |  |  | Area H&S Manager to initial. Final sign off by H&S Head of Assurance (Steve Mullins)
C2 | ITEM NO. | C2: TECHNICAL ASSURANCE FORM | Chris Binns | Chief Engineer | (020) 7126 3621 ¦ Extension: 63621 | ChrisBinns@tfl.gov.uk | Chris Binns signs the form once all items have been closed
C2 | 001 | Design of Permanent Works carried out by the Contractor. Final Design Statement FDS(b) submitted and accepted by CRL ? | (Insert Name) | Engineering Manager
C2 | 002 | Have all CPFR requirements been accepted by CRL & evidence provided in DOORS? | Milind Verma | Lead Requirements Engineer | 0203 054 3328 (Internal: 83328) | MilindVerma@crossrail.tfl.gov.uk | Sign off by Milind Verma. Evidence required for completion of item C2-001: 1. CPFR Design Verification completed and recorded in DOORS database. 2. CPFR Construction Verification completed and recorded in DOORS database
C2 | 003 | Have all design related risks related to the contract on the Project Risk Register and in ARM been closed out? | (Insert name) | Engineering Manager |  |  | Sign off by: Engineering Manager
C2 | 004 | Has evidence been provided that the works have been completed in accordance with granted design concessions? | TBC | Concessions Administrator |  | TBC | Concessions database checked by Concessions Administrator (Martin's replacement awaited).
|  |  | Nick Morgans | Head of Technical Assurance | 0203 054 0203 (Internal: 80203) | NickMorgans@crossrail.tfl.gov.uk | Sign off by Head of Assurance Nick Morgans <NickMorgans@crossrail.tfl.gov.uk>
C2 | 005 | Have all required ESM deliverables been accepted as sufficient to demonstrate ESM compliance? (i.e. has it been demonstrated that the scope of works is capable of operation to control the safety risks to future users (incl. operators & maintainers) to As Low as Reasonably Practicable (ALARP)? | Hayat Zerkani | Head of System Safety and Interoperability | T: +44 20 3054 2779 ¦ X: 82779 | HayatZerkani@crossrail.tfl.gov.uk
C2 | 006 | Has all the evidence necessary to be assessed for compliance under the Interoperability regulations been submitted to the NoBo and have you obtained an ISV or letter of support for your scope of works? | Maya Petkova | Interoperability Manager | Tel: 020 3054 2860 / Ext.82860 | MayaPetkova@crossrail.tfl.gov.uk | Contractor to demonstrate that all of CRL's TSI Interoperability Requirements for the contract have been met or are not applicable and agreement has been reached with the NoBo. Signed off by CRL's Interoperability Manager Maya Petkova
C2 | 007 | Has evidence been provided that the constructed Permanent Works comply with the Works Information (incorporating Gate 3 design, the modifications to the design instructed through PMIs post Gate 3 and accepted through the Gate Impact Review Process)? | (Insert name) | Supervisor's Rep (PFE) |  | Sign off by Supervisor's Rep | Sign off by Supervisor's Rep
C2 | 008 | Engineering Manager to confirm that all post Gate 3 changes have been subject to Gate impact Review and where required a Gate Impact Report has been prepared by the designer and accepted by CEG Head of Discipline ? | (Insert name) | Supervisor's Rep (PFE) |  | Sign off by: Engineering Manager | Sign off by: Engineering Manager
C2 | 009 | Have all NCRs & FCDs been closed out or transferred to the Defects List ? | (Insert name) | Supervisor's Rep (PFE) |  | Sign off by Supervisor's Rep | Sign off by Supervisor's Rep
C2 | 010 | Have all the Site Observations raised (including the IM observations) been closed out in the Observation data base as part of the contractual requirements? | Patrick Barry | Field Engineering Manager | 020 7126 3365 ¦ Extn: 63365 | PatrickBarry@crossrail.tfl.gov.uk | Sign off by Construction and Field Engineering Manager Patrick Barry <PatrickBarry@crossrail.tfl.gov.uk>
C2 | 011 | Has the Supervisors' Rep received a declaration from the Underground and/or Civil HoD that the Underground, Civils and Structural Verification activities have been completed? Where applicable has the Supervisors Rep received a declaration from additional relevant Discipline HoDs (including Railway Systems) that their verification activities have been completed? | (Insert / delete names) Sign off by Supervisors Rep and relevant Head of Discipline: Architecture: Julian Robinson JulianRobinson@crossrail.co.uk; M&E:Rhys Williams RhysWilliams@crossrail.co.uk; Underground: TBC Geotechnics: TBC Civils: Donal Coughlan DonalCoughlan@crossrail.co.uk; Stations: TBC | Supervisor's Rep (PFE) and / or Engineering Manager and relevant Head of Discipline | Paul Readings 0207 126 3674 (Internal: 63674) Donal Coughlan 0207 126 3709 (Internal: 63709) Julian R 0207 126 3706 (Internal: 63706) Rhys W 0207 126 3728 (Internal: 63728) | Sign off by Supervisors Rep and relevant Head of Discipline: Architecture:Julian Robinson JulianRobinson@crossrail.tfl.gov.uk; M&E:Rhys Williams RhysWilliams@crossrail.tfl.gov.uk; Underground: TBC Geotechnics: TBC Civils: Donal Coughlan DonalCoughlan@crossrail.tfl.gov.uk; Stations: TBC | Sign off by Supervisors Rep and relevant Head of Discipline: Architecture:Julian Robinson JulianRobinson@crossrail.tfl.gov.uk; M&E:Rhys Williams RhysWilliams@crossrail.tfl.gov.uk; Underground: TBC Geotechnics: TBC Civils: Donal Coughlan DonalCoughlan@crossrail.tfl.gov.uk; Stations: TBC
C2 | 012 | Have all defects that would affect use of the Works by the Employer or Others from doing their work been completed and closed out? | (Insert name) | Supervisor's Rep (PFE) |  | Sign off by Supervisor's Rep | Sign off by Supervisor's Rep
C2 | 013 | Have all the Red Line Drawings, describing the as-built asset, been submitted and accepted? | (Insert name) | Supervisor's Rep (PFE) |  | Sign off by Supervisor's Rep | Sign off by Supervisor's Rep
C2 | 014 | Has the Designer (FDC for Civils, Contractor’s Designer for D and B) completed a 'Confirmation of Red Line Drawings Certificate’? (Reference: CRL1-XRL-Z-ZFM-CR001-50009). | (Insert name) | Supervisor's Rep (PFE) |  | Sign off by: Engineering Manager | Sign off by: Engineering Manager
C2 | 015 | Have all the as-built drawings been accepted at Code 1 for Contractor designed MEPA and Railway Systems? (where applicable) | (Insert name) | Supervisor's Rep (PFE) |  | Sign off by Supervisor's Rep | Sign off by Supervisor's Rep
C2 | 016 | Has the Contractor provided acceptable as-built surveys and setting out data (i.e. control points) where required? | (Insert name) | Supervisor's Rep (PFE) |  | Sign off by Supervisor's Rep | Sign off by Supervisor's Rep
C2 | 017 | 16. Has the Chief Engineer or their representative approved the Watch and Event Items List (Ref: CRL1- XRL-Z3-ZTM-CR001-50018) produced by the S(PFE) in line with the Watch and Event Items Procedure Ref:CRL1-XRL-Z3-GPD-CR001-50017? | Chris Binns | Chief Engineer | - | ChrisBinns@tfl.gov.uk | Sign off by Chief Engineer or their representative. Evidence required completed Watch and Events list to be provided by Supervisor's Rep.
C2 | 018 | Have all RAM Documents been updated according to Data Recording and Corrective Action System (DRACAS) Records, or a plan is in place? | Richard Consterdine | Maintenance Planning Engineer | 0203 054 3178 (Internal: 83178) | RichardConsterdine@crossrail.tfl.gov.uk | RAM documentation (to be updated by T1) Component RAM Compliance Report (to be updated by CRL to confirm that actions are closed and the Component is compliant after being integrated with other assets) Contact Richard Consterdine.
C2 | 019 | Have all the DRACAS records been uploaded to the DRACAS Database and have any related actions been closed, or a plan is in place? | Richard Consterdine | Maintenance Planning Engineer | 0203 054 3178 (Internal: 83178) | RichardConsterdine@crossrail.tfl.gov.uk | DRACAS Database (on eB) updated RAM Analysis Report updated RAM Demonstration Case Report Contact Richard Consterdine
C3 | ITEM NO. | C3: PLANNING & HERITAGE | Rob Paris | Head of Sustainability & Consents | 0207 126 3943 (Internal: 63943) | robparis@crossrail.tfl.gov.uk | Rob Paris signs the form once all items have been signed off by each relevant Functional Lead
C3 | 1 | All permanent Planning and Heritage consents including any relevant Bringing-into-Use consents in place? | Julie Davis | Land Use Planning Manager | 0207 126 3951 (Internal: 63951) | JulieDavis@crossrail.tfl.gov.uk | Question signed by Julie Davis (JulieDavis@crossrail.tfl.gov.uk) once all consents as reflected on the Contractors final Consents Tracker (Code 1 on eB). Liaise with your point of contact as appropriate.
|  |  | Julie Davis | Land Use Planning Manager | 0207 126 3951 (Internal: 63951) | JulieDavis@crossrail.tfl.gov.uk
|  |  | Matthew Carney | Graduate Engineer | 0207 126 3847 (Internal: 63847) | MatthewCarney@crossrail.tfl.gov.uk
C3 | 2 | Redline / As-built drawings reviewed to confirm they are consistent with consents? | Julie Davis | Land Use Planning Manager | 0207 126 3951 (Internal: 63951) | JulieDavis@crossrail.tfl.gov.uk | Question initialled by Julie Davis (JulieDavis@crossrail.tfl.gov.uk) once it is confirmed via CCM that all consents and conditions have been discharged and the red line / as-built drawings show that constructed elements of the railway match the consented designs.
|  |  | Julie Davis | Land Use Planning Manager | 0207 126 3951 (Internal: 63951) | JulieDavis@crossrail.tfl.gov.uk
|  |  | Matthew Carney | Graduate Engineer | 0207 126 3847 (Internal: 63847) | MatthewCarney@crossrail.tfl.gov.uk
C3 | 3 | Planning and Heritage consent conditions which relate to permanent works fully discharged and complied with? | Julie Davis | Land Use Planning Manager | 0207 126 3951 (Internal: 63951) | JulieDavis@crossrail.tfl.gov.uk | Question initialled by Julie Davis (JulieDavis@crossrail.tfl.gov.uk) once evidence of compliance with consent conditions is received.
|  |  | Julie Davis | Land Use Planning Manager | 0207 126 3951 (Internal: 63951) | JulieDavis@crossrail.tfl.gov.uk
|  |  | Matthew Carney | Graduate Engineer | 0207 126 3847 (Internal: 63847) | MatthewCarney@crossrail.tfl.gov.uk
C3 | 4 | All Highway consents which may be required either for later contracts or operation transferred to relevant contractor/Crossrail? | Ben Whitton | Traffic Engineer | 0207 126 3993 (Internal: 63993) | Question initialled by Ben Whitton (BenWhitton@crossrail.tfl.gov.uk) and final sign off by Rob Paris. | Question initialled by Ben Whitton (BenWhitton@crossrail.tfl.gov.uk) and final sign off by Rob Paris.
C3 | 5 | All Temporary Highway consents closed out with all traffic management removed and highway reinstated to Highway Authority satisfaction? | Ben Whitton | Traffic Engineer | 0207 126 3993 (Internal: 63993) | Question initialled by Ben Whitton (BenWhitton@crossrail.tfl.gov.uk) and final sign off by Rob Paris. | Question initialled by Ben Whitton (BenWhitton@crossrail.tfl.gov.uk) and final sign off by Rob Paris.
C4 | ITEM NO. | C4: ENVIRONMENT | Rob Paris | Head of Sustainability & Consents | 0207 126 3943 (Internal: 63943) | robparis@crossrail.tfl.gov.uk | Rob Paris signs the form once all items have been signed off by each relevant Functional Lead
C4 | 1 | All environmental reporting data received (KPIs, recycled content, dust/air quality, noise, water, objectives and targets, carbon footprint/energy model)? | Russell Grinham | Environmental Assurance Manager | 0207 126 3935 (Internal: 63935) | RussellGrinham@crossrail.tfl.gov.uk | Question initialled by Russell Grinham and final sign off by Rob Paris.
C4 | 2 | Site Waste Management Plan completed and signed off? | Russell Grinham | Environmental Assurance Manager | 0207 126 3935 (Internal: 63935) | RussellGrinham@crossrail.tfl.gov.uk | Question initialled by Russell Grinham and final sign off by Rob Paris.
C4 | 3 | Survey information handed over (contaminated land, ecology)? | Russell Grinham | Environmental Assurance Manager | 0207 126 3935 (Internal: 63935) | RussellGrinham@crossrail.tfl.gov.uk | Question initialled by Russell Grinham and final sign off by Rob Paris.
C4 | 4 | Contaminated land verification report accepted? | Russell Grinham | Environmental Assurance Manager | 0207 126 3935 (Internal: 63935) | RussellGrinham@crossrail.tfl.gov.uk | Question initialled by Russell Grinham and final sign off by Rob Paris.
C4 | 5 | Maintenance regime for site (incl landscaping, knotweed management) handed over? | Russell Grinham | Environmental Assurance Manager | 0207 126 3935 (Internal: 63935) | RussellGrinham@crossrail.tfl.gov.uk | Question initialled by Russell Grinham and final sign off by Rob Paris.
C4 | 6 | All CARs, NCRs, and incident investigations closed out? | Russell Grinham | Environmental Assurance Manager | 0207 126 3935 (Internal: 63935) | RussellGrinham@crossrail.tfl.gov.uk | Question initialled by Russell Grinham and final sign off by Rob Paris.
C4 | 7 | Environmental design checklists for works complete? | Russell Grinham | Environmental Assurance Manager | 0207 126 3935 (Internal: 63935) | RussellGrinham@crossrail.tfl.gov.uk | Question initialled by Russell Grinham and final sign off by Rob Paris.
C4 | 8 | Archaeological archive information received (archaeological works only)? | Russell Grinham | Environmental Assurance Manager | 0207 126 3935 (Internal: 63935) | RussellGrinham@crossrail.tfl.gov.uk | Question initialled by Russell Grinham and final sign off by Rob Paris.
C4 | 9 | Boreholes decommissioned or agreed as permanent monitoring locations and handed over? | Russell Grinham | Environmental Assurance Manager | 0207 126 3935 (Internal: 63935) | RussellGrinham@crossrail.tfl.gov.uk | Question initialled by Russell Grinham and final sign off by Rob Paris.
C4 | 10 | CEEQUAL assessment completed and submitted or BREEAM assessment completed and submitted? | Russell Grinham | Environmental Assurance Manager | 0207 126 3935 (Internal: 63935) | RussellGrinham@crossrail.tfl.gov.uk | Question initialled by Russell Grinham and final sign off by Rob Paris.
C4 | 11 | Have post construction actions associated with BREEAM/CEEQUAL been clearly communicated to/documentation has been made available to the operator, e.g. requirements for seasonal commissioning, Building User Guide? | Russell Grinham | Environmental Assurance Manager | 0207 126 3935 (Internal: 63935) | RussellGrinham@crossrail.tfl.gov.uk | Question initialled by Russell Grinham and final sign off by Rob Paris.
C4 | 12 | Environmental Agency has confirmed that the works which were approved under Schedule 17 Part 3? | Russell Grinham | Environmental Assurance Manager | 0207 126 3935 (Internal: 63935) | RussellGrinham@crossrail.tfl.gov.uk | Question initialled by Russell Grinham and final sign off by Rob Paris.
C4 | 13 | British Waterways Board has confirmed that the works which were approved un Schedule 17 Part 4? | Russell Grinham | Environmental Assurance Manager | 0207 126 3935 (Internal: 63935) | RussellGrinham@crossrail.tfl.gov.uk | Question initialled by Russell Grinham and final sign off by Rob Paris.
C4 | 14 | Port of London Authority has confirmed that the works which were approved under Schedule 17 Part 5? | Russell Grinham | Environmental Assurance Manager | 0207 126 3935 (Internal: 63935) | RussellGrinham@crossrail.tfl.gov.uk | Question initialled by Russell Grinham and final sign off by Rob Paris.
C4 | 15 | All discharge consents which may be required either for later contracts or operation transferred to relevant contractor/Crossrail? | Russell Grinham | Environmental Assurance Manager | 0207 126 3935 (Internal: 63935) | RussellGrinham@crossrail.tfl.gov.uk | Question initialled by Russell Grinham and final sign off by Rob Paris.
C5 | ITEM NO. | C5: UNDERTAKINGS & ASSURANCES | Rob Paris | Head of Sustainability & Consents | 0207 126 3943 (Internal: 63943) | robparis@crossrail.tfl.gov.uk | Rob Paris signs the form once all items have been signed off by Olabowale Ogunsanya
C5 | 1 | Have all applicable U&As been discharged or handed over in accordance with the accepted Commitments Compliance Plan? | Olabowale Ogunsanya | Commitments Compliance Officer | 0207 126 3933 (Internal: 63933) | OlabowaleOgunsanya@crossrail.tfl.gov.uk | Question initialled by Olabowale Ogunsanya when all commitments on the Commitments Tracker have been closed.
C5 | 2 | Has all commitments compliance evidence uploaded into CDT? | Olabowale Ogunsanya | Commitments Compliance Officer | 0207 126 3933 (Internal: 63933) | OlabowaleOgunsanya@crossrail.tfl.gov.uk | Question initialled by Olabowale Ogunsanya when all commitments on the Commitments Tracker have been closed.
C6 | ITEM NO. | C6: ESTATES | Paul Bolton - | Head of Estates Land ＆ Property | 0207 126 1997 (Internal: 61997) | PaulBolton@crossrail.tfl.gov.uk | Individual items signed by Gus Kerswell or Judith Slater. Form signed by Paul Bolton when all items are signed off
C6 | 1 | The site area has been handed back via the hand-back and hand-over certification process in a clean, secure and vacant condition (where necessary) and the new receiving party is identified? | Renae Jessup / Gus Kerswell / Judith Slater | Estates Officer | Renae - 0203 054 7601 (Internal: 87601)) Gus - 0207 126 2217 (Internal: 62217) Judith - 0207 126 1982 (Internal: 61982) | RenaeJessup@crossrail.tfl.gov.uk GusKerswell@crossrail.tfl.gov.uk JudithSlater@crossrail.tfl.gov.uk | Question initialled by Renae Jessup / Gus Kerswell / Judith Slater and final sign off by Paul Bolton
C6 | 2 | Boundary fences as specified in places where necessary? | Renae Jessup / Gus Kerswell / Judith Slater | Estates Officer | Renae - 0203 054 7601 (Internal: 87601)) Gus - 0207 126 2217 (Internal: 62217) Judith - 0207 126 1982 (Internal: 61982) | RenaeJessup@crossrail.tfl.gov.uk GusKerswell@crossrail.tfl.gov.uk JudithSlater@crossrail.tfl.gov.uk | Question initialled by Renae Jessup / Gus Kerswell / Judith Slater and final sign off by Paul Bolton
C6 | 3 | Utility meters clearly stated, jointly read, contract accounts paid and closed by contractors and identified where live for transfer? | Renae Jessup / Gus Kerswell / Judith Slater | Estates Officer | Renae - 0203 054 7601 (Internal: 87601)) Gus - 0207 126 2217 (Internal: 62217) Judith - 0207 126 1982 (Internal: 61982) | RenaeJessup@crossrail.tfl.gov.uk GusKerswell@crossrail.tfl.gov.uk JudithSlater@crossrail.tfl.gov.uk | Question initialled by Renae Jessup / Gus Kerswell / Judith Slater and final sign off by Paul Bolton
C6 | 4 | The site and any remaining structure, plant or equipment, left in a secure condition to prevent unauthorised entry, damage or misuse? | Renae Jessup / Gus Kerswell / Judith Slater | Estates Officer | Renae - 0203 054 7601 (Internal: 87601)) Gus - 0207 126 2217 (Internal: 62217) Judith - 0207 126 1982 (Internal: 61982) | RenaeJessup@crossrail.tfl.gov.uk GusKerswell@crossrail.tfl.gov.uk JudithSlater@crossrail.tfl.gov.uk | Question initialled by Renae Jessup / Gus Kerswell / Judith Slater and final sign off by Paul Bolton
C7 | ITEM NO. | C7: RAIL INTERFACES | Fawad Munir | Rail Interface Manager/T&C Possession | 0207 126 3385 (Internal: 63385) 07734968752 | FawadMunir@crossrail.tfl.gov.uk | Individual items signed by the site representative who manages the relationship with the third party IM. Once all applicable items have been finalised Fawad Munir signs the form.
C7 | 1 | Has the Site Rep obtained confirmation that the relevant LU Infrastructure Manager is satisfied that the necessary Assurances have been provided in relation to this contract? | (Insert name) | Site Representative dealing with the LU interface |  |  | Item signed by Site Representative dealing with 3rd Party. Overall Sign off by Fawad Munir <FawadMunir@crossrail.tfl.gov.uk>
C7 | 1 | Has the Site Rep obtained confirmation that the relevant NR Infrastructure Manager is satisfied that the necessary Assurances have been provided in relation to this contract? | (Insert name) | Site Representative dealing with the NR interface |  |  | Item signed by Site Representative dealing with 3rd Party. Overall Sign off by Fawad Munir <FawadMunir@crossrail.tfl.gov.uk>
C7 | 1 | Has the Site Rep obtained confirmation that the relevant DLR Infrastructure Manager is satisfied that the necessary Assurances have been provided in relation to this contract? | (Insert name) | Site Representative dealing with the DLR interface |  |  | Item signed by Site Representative dealing with 3rd Party. Overall Sign off by Fawad Munir <FawadMunir@crossrail.tfl.gov.uk>
C7 | 1 | Has the Site Rep obtained confirmation that the relevant LO Infrastructure Manager is satisfied that the necessary Assurances have been provided in relation to this contract? | (Insert name) | Site Representative dealing with the LO interface |  |  | Item signed by Site Representative dealing with 3rd Party. Overall Sign off by Fawad Munir <FawadMunir@crossrail.tfl.gov.uk>
C7 | 2 | Has the Site Rep obtained confirmation that LU 3rd Party Infrastructure Manager got any issues that would indicate that these works cannot be successfully integrated to deliver the completed railway been either resolved or identified for resolution? | (Insert name) | Site Representative dealing with the LU interface |  |  | Item signed by Site Representative dealing with 3rd Party. Overall Sign off by Fawad Munir <FawadMunir@crossrail.tfl.gov.uk>
C7 | 2 | Has the Site Rep obtained confirmation that NR 3rd Party Infrastructure Manager got any issues that would indicate that these works cannot be successfully integrated to deliver the completed railway been either resolved or identified for resolution? | (Insert name) | Site Representative dealing with the NR interface |  |  | Item signed by Site Representative dealing with 3rd Party. Overall Sign off by Fawad Munir <FawadMunir@crossrail.tfl.gov.uk>
C7 | 2 | Has the Site Rep obtained confirmation that DLR 3rd Party Infrastructure Manager got any issues that would indicate that these works cannot be successfully integrated to deliver the completed railway been either resolved or identified for resolution? | (Insert name) | Site Representative dealing with the DLR interface |  |  | Item signed by Site Representative dealing with 3rd Party. Overall Sign off by Fawad Munir <FawadMunir@crossrail.tfl.gov.uk>
C7 | 2 | Has the Site Rep obtained confirmation that LO 3rd Party Infrastructure Manager got any issues that would indicate that these works cannot be successfully integrated to deliver the completed railway been either resolved or identified for resolution? | (Insert name) | Site Representative dealing with the LO interface |  |  | Item signed by Site Representative dealing with 3rd Party. Overall Sign off by Fawad Munir <FawadMunir@crossrail.tfl.gov.uk>
C8 | ITEM NO. | C8: SYSTEMWIDE | Darren Coleman | Systemwide Delivery Director | 020 3229 9318 | darrencoleman@crossrail. tfl.gov.uk | Colin Gainsford signs the form once Howard Crane (Supervisor's Representative) has signed all items.
C8 | 1 | Has the Contractor provided records / As Built drawings / Red-line drawings for interfaces with Systemwide and have these documents been through an acceptance review where required? | Howard Crane | Supervisor's Rep (PFE) | 0207 126 2689 (Internal: 62689) | HowardCrane@crossrail.tfl.gov.uk | N/A - Please refer the procedure Employer's Completion Process CRL1-XRL-O4-GPD-CR001-50018 Rev 8.0.
C8 | 2 | Has the Contractor provided acceptable as built surveys and setting out data (i.e. control points) where required? | Howard Crane | Supervisor's Rep (PFE) | 0207 126 2689 (Internal: 62689) | HowardCrane@crossrail.tfl.gov.uk | N/A - Please refer the procedure Employer's Completion Process CRL1-XRL-O4-GPD-CR001-50018 Rev 8.0.
C8 | 3 | Has the Contractor provided acceptable Health & Safety Files in cases where that Contractor's civil structure is being taken over by Systemwide for fit-out activities? Files to include records and arrangements of all temporary facilities left in place. | Howard Crane | Supervisor's Rep (PFE) | 0207 126 2689 (Internal: 62689) | HowardCrane@crossrail.tfl.gov.uk | N/A - Please refer the procedure Employer's Completion Process CRL1-XRL-O4-GPD-CR001-50018 Rev 8.0.
C9 | ITEM NO. | C9: TECHNICAL INFORMATION | (Chris Binns) - Chief Engineer / (TBC) Head of Technical Information | Chief Engineer / Head of Technical Information | Chris Binns | Chris Binns | Chris Binns signs off C9 form after all items have been closed and signed off by the individual item owners
C9 | 1 | Have all eB CMDL deliverables been created? | Varsha Ruchaya | Document and Data Compliance Controller | T 020 7126 4373 auto 64373 | VarshaRuchaya@crossrail.tfl.gov.uk | Question initialled by Varsha Ruchaya and final sign off by Chris Binns.
C9 | 2 | Have all eB CMDL deliverables been delivered? | Varsha Ruchaya | Document and Data Compliance Controller | T 020 7126 4373 auto 64373 | VarshaRuchaya@crossrail.tfl.gov.uk | Question initialled by Varsha Ruchaya and final sign off by Chris Binns.
C9 | 3 | Are there any Obsolete/Cancelled Crossrail deliverables required to be re-instated? If so, have these all been submitted and accepted formally?’ | Varsha Ruchaya | Document and Data Compliance Controller | T 020 7126 4373 auto 64373 | VarshaRuchaya@crossrail.tfl.gov.uk | Question initialled by Varsha Ruchaya and final sign off by Chris Binns.
C9 | 4 | Is all eB deliverable documentation identifiable, legible and retrievable? | Varsha Ruchaya | Document and Data Compliance Controller | T 020 7126 4373 auto 64373 | VarshaRuchaya@crossrail.tfl.gov.uk | Question initialled by Varsha Ruchaya and final sign off by Chris Binns.
C9 | 5 | Have all completed eB CMDL deliverables been supported by a signed Code 1 or 4 Decal (excl. WCCC)? | Varsha Ruchaya | Document and Data Compliance Controller | T 020 7126 4373 auto 64373 | VarshaRuchaya@crossrail.tfl.gov.uk | Question initialled by Varsha Ruchaya and final sign off by Chris Binns.
C9 | 6 | With respect to the WCCC, are the outstanding works / defects including the outstanding deliverables (if any) listed on the COWL? Is the COWL accepted and coded Code 1? | Varsha Ruchaya | Document and Data Compliance Controller | T 020 7126 4373 auto 64373 | VarshaRuchaya@crossrail.tfl.gov.uk | Question initialled by Varsha Ruchaya and final sign off by Chris Binns.
C9 | 7 | Is all Asset Tag Label & Equipment Label Installation complete? | Mark Houghton | Asset Information Provision Manager | T 0207 126 3468 (Auto 63468) | MarkHoughton@crossrail.tfl.gov.uk | Question initialled by Mark Houghton and final sign off by Chris Binns.
C9 | 008 | Is the information on the Asset Register for this contract 100% complete, including all asset attributes and relationships? | Mark Houghton | Asset Information Provision Manager | T 0207 126 3468 (Auto 63468) | MarkHoughton@crossrail.tfl.gov.uk | Question initialled by Mark Houghton and final sign off by Chris Binns.
C9 | 08 - a) | a) Have all Asset Tag IDs been named? | Mark Houghton | Asset Information Provision Manager | T 0207 126 3468 (Auto 63468) | MarkHoughton@crossrail.tfl.gov.uk | Question initialled by Mark Houghton and final sign off by Chris Binns.
C9 | 08- b) | b) Have all named asset tags been related to the Asset Breakdown Structure (ABS), to Rooms/Spaces, to Asset Owners and Design Alternative Asset IDs (DAAIDs)? | Mark Houghton | Asset Information Provision Manager | T 0207 126 3468 (Auto 63468) | MarkHoughton@crossrail.tfl.gov.uk | Question initialled by Mark Houghton and final sign off by Chris Binns.
C9 | 08- c) | c) has all serialised equipment been assigned against asset tag IDs? | Mark Houghton | Asset Information Provision Manager | T 0207 126 3468 (Auto 63468) | MarkHoughton@crossrail.tfl.gov.uk | Question initialled by Mark Houghton and final sign off by Chris Binns.
C9 | 08- d) | d) are the asset attributes complete? | Mark Houghton | Asset Information Provision Manager | T 0207 126 3468 (Auto 63468) | MarkHoughton@crossrail.tfl.gov.uk | Question initialled by Mark Houghton and final sign off by Chris Binns.
C9 | 009 | Is the As Built 3D Master Model and associated 3D Model Issues Report accepted as code 1? | Brian Evans | Senior 3D/4D Model Compliance Coordinator | 0207 126 4387 (Internal: 64387) | BrianEvans@crossrail.tfl.gov.uk | Question initialled by Brian Evans and final sign off by Chris Binns.
C9 | 010 | Are all As Built drawings accepted as code 1? | Brian Evans | Senior 3D/4D Model Compliance Coordinator | 0207 126 4387 (Internal: 64387) | BrianEvans@crossrail.tfl.gov.uk | Question initialled by Brian Evans and final sign off by Chris Binns.
C9 | 011 | Is the design in accordance with CRL CAD standards and CAD related requirements within the Works Information? | Brian Evans | Senior 3D/4D Model Compliance Coordinator | 0207 126 4387 (Internal: 64387) | BrianEvans@crossrail.tfl.gov.uk | Question initialled by Brian Evans Andy and final sign off by Chris Binns.
C9 | 012 | Have all the O&M Deliverables and Manuals been submitted by the Contractor, accepted by the Supervisor’s Rep (PFE) and are they in compliance with CRL requirements? | Ian Macdonald | Handover Information Manager | 0207 126 3523 (Internal: 63523) | IanMacdonald@crossrail.tfl.gov.uk | Question initialled by Ian MacDonald and final sign off by Chris Binns.
C9 | 013 | Is all O&M deliverable information available to enable CRL to add all O&M deliverables to the Operational and Maintenance structure on eB and link them to the O&M manuals? | Ian Macdonald | Handover Information Manager | 0207 126 3523 (Internal: 63523) | IanMacdonald@crossrail.tfl.gov.uk | Question initialled by Ian MacDonald and final sign off by Chris Binns.
C10 | ITEM NO. | C10: Third Party Agreements | Richard Ellis - Head of Agreement Management | Head of Agreement Management | 0207 126 2863 (Internal: 62863) | RichardEllis@crossrail.tfl.gov.uk | Richard Ellis signs off C10 form after all agreements have been closed on the agreements tracker and/or responsibility for managing the agreement has been transferred to a new agreement manager. signed off by
C10 | 1 | All Third Party Agreements that relate to this Contract have been identified by reference to the Agreements Management System and there are no outstanding duties or obligations which would prevent finalisation of the closure process as it relates to the Contract. | Esme Hobbs | Agreements Manager | 0207 126 2875 (Internal: 62875) | EsmeHobbs@crossrail.tfl.gov.uk | Question initialled by Esme Hobbs or Simon Pope and final sign off by Richard Ellis.
C10 | 2 | All Third Party Agreements in Identity and Create stages that relate to this Contract have been identified by reference to the Agreements Management System and there are no outstanding actions which would prevent finalisation of the closure process as it relates to the Contract. | Esme Hobbs | Agreements Manager | 0207 126 2875 (Internal: 62875) | EsmeHobbs@crossrail.tfl.gov.uk | Question initialled by Esme Hobbs or Simon Pope and final sign off by Richard Ellis.
C10 | 3 | A Transfer Handover Meeting has been held with the CRL Agreements Team and the Infrastructure Manager (RFL / LU) who will be taking over management accountability for Third Party Agreement Interfaces at this location. | Esme Hobbs | Agreements Manager | 0207 126 2875 (Internal: 62875) | EsmeHobbs@crossrail.tfl.gov.uk | Question initialled by Esme Hobbs or Simon Pope and final sign off by Richard Ellis.
C20 | ITEM NO. | C20: Completion | Piotr Swieboda | Completion Manager | 0207 126 4039 (Internal: 64039) 07926 100380 | PiotrSwieboda@crossrail.tfl.gov.uk | Completion Manager signs the form after all items have been signed off by the Supervisor's Rep, the PM and the FE Manager.
C20 | 1 | Is the work complete or outstanding works listed on the Consolidated Outstanding Works List (COWL) | Supervisor's Rep (PFE) (Insert name) |  |  |  | Question initialled by Supervisor’s Rep and final sign off by Completion Manager Piotr Swieboda
C20 | 2 | Have all CARs, NCRs FCDs & RFIs been properly closed out or listed on the COWL? | Supervisor's Rep (PFE) (Insert name) |  |  |  | Question initialled by Supervisor’s Rep and final sign off by Completion Manager Piotr Swieboda
C20 | 3 | Has the C-ICD document or Handover Plan been submitted by the Contractor and accepted by CRL | Supervisor's Rep (PFE) (Insert name) |  |  |  | Question initialled by Supervisor’s Rep and final sign off by Completion Manager Piotr Swieboda
C20 | 4 | Have all packages been completed and Construction Certificates signed off? | Certification Manager | Judith Griffiths | 07411009264 | JudithGriffiths@crossrail.tfl.gov.uk | Question initialled by Lead Certification Manager and final sign off by Completion Manager Piotr Swieboda
C20 | 5 | Have all functional heads completed their review of this contract and signed off their Checklist? | Piotr Swieboda | Completion Manager | 0207 126 4039 (Internal: 64039) 07926 100380 | PiotrSwieboda@crossrail.tfl.gov.uk | Question initialled by Completion Manager (Piotr Swieboda)
C20 | 6 | Has all work scope removed from the current contract been formally transferred to the follow-on contract? Or alternatively has all work scope removed from the current contract been formally accepted by the end user for instances where there is no follow-on contract? Note: List of items de-scoped and transferred/accepted to be attached as evidence. | Project Manager (Insert name) |  |  | Question initialled by Project Manager | Question initialled by Project Manager
C20 | 7 | Does the Contractor have a Care and Maintenance Plan which has been reviewed by CEG and accepted by the CRL Project Manager? | Project Manager (Insert name) |  |  | Signed by CRL project manager | Signed by CRL project manager
C20 | 8 | Has the CRL Project Manager agreed/clarified all handover matters with the Care and Maintenance Manager? | Project Manager (Insert name) |  |  | Singed by CRL PM and the Care Maintenance Manager. | Singed by CRL PM and the Care Maintenance Manager.
C20 | 9 | Has provision been made for Supervisor’s cover during the Defects Liability Period ? | Piotr Swieboda | Completion Manager | 0207 126 4039 (Internal: 64039) 07926 100380 | PiotrSwieboda@crossrail.tfl.gov.uk | Question initialled by Completion Manager
C20 | 10 | Have all the Site Observations raised (including the IM observations) been closed out in the Observation data base as part of the contractual requirements? | Patrick Barry | Field Engineering Manager / Handover Manager | 0207 126 3365 (Internal: 63365) | Question initialled by Construction and Field Engineering Manager Patrick Barry | Question initialled by Construction and Field Engineering Manager Patrick Barry
C20 | 11 | Have all the interfaces with utility providers been closed out? | Patrick Barry | Field Engineering Manager / Handover Manager | 0207 126 3365 (Internal: 63365) | Question initialled by Construction and Field Engineering Manager Patrick Barry | Question initialled by Construction and Field Engineering Manager Patrick Barry
C20 | 012 | Has the contractor delivered all training in accordance with the agreed Training Strategy and Plan? | (Insert Name) | CRL Handover Lead / Operational Readiness Training |  | Sign off by CRL Handover Lead / Operational Readiness Training Manager
C30 | ITEM NO. | C30: Authorisation to Accept WCCC | Piotr Swieboda | Completion Manager | 0207 126 4039 (Internal: 64039) 07926 100380 | PiotrSwieboda@crossrail.tfl.gov.uk | Signed by the Completion Manager when all forms have been signed by the Function Lead.
C30 | 1 | Completion Manager (Piotr Swieboda) or the Supervisor (Chris Titterton) to issue form C30 authorising acceptance of WCCC or SCCC once all the C1-C20 forms have been signed off. | Piotr Swieboda | Completion Manager | 0207 126 4039 (Internal: 64039) 07926 100380 | PiotrSwieboda@crossrail.tfl.gov.uk | Sign off by the Completion Manager (Piotr Swieboda) or the Supervisor (Allen Lee-John).
Note on F2: v_JohnsonMonteiro: Phone numbers might have changed due to Office move etc.

## # 2 ECP Contacts List (hidden)
Contact List for the Employers Completion Process (ECP) for CXXX Contract Completion
FORM | ITEM NO. | QUESTION | Point of contact | Role | Telephone Number | Email address | Sign off process notes.
C1 | ITEM NO. | C1: HEALTH &SAFETY | Mark Lawrence | Head of Health and Safety Assurance |  | MarkLawrence1@crossrail.tfl.gov.uk | Mark Lawrence signs the form once all items have been closed
C1 | 1 | Has the Health and Safety File (as defined in the Construction (Design and Management Regulations 2015) been handed over and evaluated by the Area Health and Safety Manager as meeting CRLs requirements and coded 1 by the CRL site team. The requirements include specifically to have the seven H and S File elements of information as defined in the Health and Safety File Template ref. CR-XRL-Z7-ZTM-CR001-50001. These sections are also to be cross referenced as separate documents to the corresponding seven sections of the MDL Structure. Health and Safety File – C05.003. | (Insert Name) | H&S Generalist / CDM Integrator - TBC | (Insert Phone) | (Insert Email ID) | H&S Generalist to initial. Final sign off by Head of Core Health & Safety or Deputy. CDM Integrator to provide guidance on the make up of the H+S file. Can be included as a reviewer prior to approval to avoid two reviews one from site and one from H&S Assurance. CDM Integrator (TBC) can also provide Guidance on other CDM requirements if necessary. ( Point 6 Cert)
C1 | 002 | Has the site and any structure, plant (fixed or portable) or equipment, been left in a safe condition? | (Insert Name) | H&S Generalist | - | - | H&S Generalist to initial. Final sign off by Head of Core Health & Safety or Deputy.
C1 | 003 | Is the site and any remaining structure, plant or equipment, left in a secure condition to prevent unauthorised entry, damage or misuse ? | (Insert Name) | H&S Generalist | - | - | H&S Generalist to initial. Final sign off by Head of Core Health & Safety or Deputy.
C1 | 004 | Has the CDM Control Point 6 (Works Completion) Certificate been issued (not applicable for sectional completions)? | (Insert Name) | H&S Generalist | - | - | H&S Generalist to initial. Final sign off by Head of Core Health & Safety or Deputy.
C1 | 005 | Have the above questions been closed out to the satisfaction of CRL Sector Health & Safety Manager? | Steve Mullins | Head of Programme H&S | - | Mullins Steve <SteveMullins@crossrail.tfl.gov.uk> | Head of Programme H&S to initial. Final sign off by Head of Core Health & Safety Deputy.
C2 | ITEM NO. | C2: TECHNICAL ASSURANCE FORM | Chris Binns | Chief Engineer | (020) 7126 3621 ¦ Extension: 63621 | ChrisBinns@tfl.gov.uk | Chris Binns signs the form once all items have been closed
C2 | 001 | Design of Permanent Works carried out by the Contractor. Final Design Statement FDS(b) submitted and accepted by CRL ? | (Insert Name) | Engineering Manager | - | - | -
C2 | 002 | Have all CPFR requirements been accepted by CRL & evidence provided in DOORS? | Milind Verma | Lead Requirements Engineer | 0203 054 3328 (Internal: 83328) | MilindVerma@crossrail.tfl.gov.uk | Sign off by Milind Verma. Evidence required for completion of item C2-001: 1. CPFR Design Verification completed and recorded in DOORS database. 2. CPFR Construction Verification completed and recorded in DOORS database
C2 | 003 | Have all design related risks related to the contract on the Project Risk Register been closed out? | (Insert name) | Engineering Manager | - | - | Sign off by: Engineering Manager
C2 | 004 | Have all applications for Concessions against Baseline Standards been granted and any specified conditions closed? | Nick Morgans | Concessions Administrator Head of Technical Assurance | 0203 054 0203 (Internal: 80203) | NickMorgans@crossrail.tfl.gov.uk | Concessions database checked by Concessions Administrator. Provide reference to the Concessions Tracker. Sign off by Head of Assurance Nick Morgans <NickMorgans@crossrail.tfl.gov.uk>
C2 | 005 | Have all required ESM deliverables been accepted as sufficient to demonstrate ESM compliance? (i.e. has it been demonstrated that the scope of works is capable of operation to control the safety risks to future users (incl. operators & maintainers) to As Low as Reasonably Practicable (ALARP)? | Hayat Zerkani | Head of System Safety and Interoperability | T: +44 20 3054 2779 ¦ X: 82779 | HayatZerkani@crossrail.tfl.gov.uk | -
C2 | 006 | Has all the evidence necessary to be assessed for compliance under the Interoperability regulations been submitted to the NoBo and have you obtained an ISV or letter of support for your scope of works? | Maya Petkova | Interoperability Manager | Tel: 020 3054 2860 / Ext.82860 | MayaPetkova@crossrail.tfl.gov.uk | Contractor to demonstrate that all of CRL's TSI Interoperability Requirements for the contract have been met or are not applicable and agreement has been reached with the NoBo. Signed off by CRL's Interoperability Manager Maya Petkova
C2 | 007 | Has evidence been provided that the constructed Permanent Works comply with the Works Information (incorporating Gate 3 design, the modifications to the design instructed through PMIs post Gate 3 and accepted through the Gate Impact Review Process)? | (Insert name) | Supervisor's Rep (PFE) | - | Sign off by Supervisor's Rep | Sign off by Supervisor's Rep
C2 | 008 | Engineering Manager to confirm that all post Gate 3 changes have been subject to Gate impact Review and where required a Gate Impact Report has been prepared by the designer and accepted by CEG Head of Discipline ? | (Insert name) | Supervisor's Rep (PFE) | - | Sign off by: Engineering Manager | Sign off by: Engineering Manager
C2 | 009 | Have all NCRs & FCDs been closed out or transferred to the Defects List ? |  |  | - | Sign off by Supervisor's Rep | Sign off by Supervisor's Rep
C2 | 010 | Have all observations recorded on EOWL (CRL and IM observations) related to contract’s scope have been either closed out OR added to the COWL as punchwork items so that they remain a contractual obligation of the contractor? | (Insert name) | Supervisor's Rep (PFE) | - | Sign off by Supervisor's Rep | Sign off by Supervisor's Rep
C2 | 011 | Handover Team to confirm their acceptance of the Supervisor’s Rep’s statement above (Observations closure). | Patrick Barry | Handover Manager – Central Section Patrick Barry | - | Barry Patrick <PatrickBarry@crossrail.tfl.gov.uk> | To be confirmed by the Supervisor's Rep (PFE) and the PTR / EOWL database cross checked by the Handover Manager
C2 | 012 | Has the Supervisors’ Rep received a declaration from the Underground and/or Civil HoD that the Underground, Civils and Structural Verification activities (VAPs) have been completed? Where applicable has the Supervisors Rep received a declaration from additional relevant Discipline HoDs (including Railway Systems) that their verification activities have been completed? | (Insert / delete names) Sign off by relevant Head of Discipline: Architecture: Julian Robinson JulianRobinson@crossrail.co.uk; MEP (incl. Fire and Routewide M&E where applicable) Rhys Williams:Rhys Williams RhysWilliams@crossrail.co.uk; Civil & Structural Donal Coughlan DonalCoughlan@crossrail.co.uk | Supervisor's Rep (PFE) and / or Engineering Manager and relevant Head of Discipline | Paul Readings 0207 126 3674 (Internal: 63674) Donal Coughlan 0207 126 3709 (Internal: 63709) Julian R 0207 126 3706 (Internal: 63706) Rhys W 0207 126 3728 (Internal: 63728) | Sign off by relevant Head of Discipline: Architecture:Julian Robinson JulianRobinson@crossrail.tfl.gov.uk; M&E:Rhys Williams RhysWilliams@crossrail.tfl.gov.uk; Civils & Stations: Donal Coughlan DonalCoughlan@crossrail.co.uk | Sign off by relevant Head of Discipline: Architecture:Julian Robinson JulianRobinson@crossrail.tfl.gov.uk; M&E:Rhys Williams RhysWilliams@crossrail.tfl.gov.uk; Civils & Stations: Donal Coughlan DonalCoughlan@crossrail.tfl.gov.uk;
C2 | 013 | Have all the Red Line Drawings, describing the as-built asset, been submitted and accepted? | (Insert name) | Supervisor's Rep (PFE) | - | Sign off by Supervisor's Rep | Sign off by Supervisor's Rep
C2 | 014 | Has the Designer (FDC for Civils, Contractor’s Designer for D and B) completed a 'Confirmation of Red Line Drawings Certificate’? (Reference: CRL1-XRL-Z-ZFM-CR001-50009). | (Insert name) | Supervisor's Rep (PFE) / Engineering Manager | - | Sign off by: Engineering Manager | Sign off by: Engineering Manager
C2 | 015 | Have all the as-built drawings been accepted at Code 1 for Contractor designed MEPA and Railway Systems? (where applicable) | (Insert name) | Supervisor's Rep (PFE) | - | Sign off by Supervisor's Rep | Sign off by Supervisor's Rep
C2 | 016 | Has the Contractor provided acceptable as-built surveys and setting out data (i.e. control points) where required? | (Insert name) | Supervisor's Rep (PFE) | - | Sign off by Supervisor's Rep | Sign off by Supervisor's Rep
C2 | 017 | 16. Has the Chief Engineer or their representative approved the Watch and Event Items List (Ref: CRL1- XRL-Z3-ZTM-CR001-50018) produced by the S(PFE) in line with the Watch and Event Items Procedure Ref:CRL1-XRL-Z3-GPD-CR001-50017? | Chris Binns | Chief Engineer | - | ChrisBinns@tfl.gov.uk | Sign off by Chief Engineer or their representative. Approved Watch and Events items list to be provided by Supervisor's Rep.
C2 | 018 | Have all RAM Documents been updated according to Data Recording and Corrective Action System (DRACAS) Records, or a plan is in place? | Richard Consterdine | RAM Engineer or Lead Reliability Engineer | 0203 054 3178 (Internal: 83178) | RichardConsterdine@crossrail.tfl.gov.uk | RAM documentation (to be updated by T1) Component RAM Compliance Report (to be updated by CRL to confirm that actions are closed and the Component is compliant after being integrated with other assets) Contact Richard Consterdine.
C2 | 019 | Have all the DRACAS records been uploaded to the DRACAS Database and have any related actions been closed, or a plan is in place? | Richard Consterdine | RAM Engineer or Lead Reliability Engineer | 0203 054 3178 (Internal: 83178) | RichardConsterdine@crossrail.tfl.gov.uk | DRACAS Database (on eB) updated RAM Analysis Report updated RAM Demonstration Case Report Contact Richard Consterdine
C2 | 020 | Has the technical content of the COWL been consulted and confirmed with the Chief Engineer or delegate? | Chris Binns | Chief Engineer or delegate |  | ChrisBinns@tfl.gov.uk | Sign-off by the Chief Engineer / delegate. COWL reference to be provided
C2 | 021 | Has the Cyber Security Information provided by the Contractor for Element Completion Handover Report (ECHR) been accepted Code 1 by CRL? | Justin Stenner | Chief Information Security Officer | - | Sign-off by Chief Information Security Officer (Justin Stenner) | Confirmation by SR. Sign-off by Chief Information Security Officer (CISO). Cyber Security Information - Code 1 ECHR reference to be provided.
C2 | 022 | Have all applications for Concessions against Baseline Standards been granted and any specified conditions closed? | Nick Morgans | Concessions Administrator Head of Technical Assurance | 0203 054 0203 (Internal: 80203) | NickMorgans@crossrail.tfl.gov.uk | Provide reference to CARE report to support the ECP. Email confirmation from Concessions Administrator. Sign off by Head of Assurance Nick Morgans <NickMorgans@crossrail.tfl.gov.uk>
C3 | ITEM NO. | C3: PLANNING & HERITAGE | Rob Paris | Head of Sustainability & Consents | 0207 126 3943 (Internal: 63943) | robparis@crossrail.tfl.gov.uk | Rob Paris signs the form once all items have been signed off by each relevant Functional Lead
C3 | 001 | All permanent Planning and Heritage consents including any relevant Bringing-into-Use consents in place? | Julie Davis Matthew Carney | Land Use Planning Manager Graduate Engineer | 0207 126 3951 (Internal: 63951) 0207 126 3847 (Internal: 63847) | JulieDavis@crossrail.tfl.gov.uk MatthewCarney@crossrail.tfl.gov.uk | Question signed by Julie Davis (JulieDavis@crossrail.tfl.gov.uk) once all consents as reflected on the Contractors final Consents Tracker (Code 1 on eB). Liaise with your point of contact as appropriate.
C3 | 002 | Redline / As-built drawings reviewed to confirm they are consistent with consents? | Julie Davis Matthew Carney | Land Use Planning Manager Graduate Engineer | 0207 126 3951 (Internal: 63951) 0207 126 3847 (Internal: 63847) | JulieDavis@crossrail.tfl.gov.uk MatthewCarney@crossrail.tfl.gov.uk | Question initialled by Julie Davis (JulieDavis@crossrail.tfl.gov.uk) once it is confirmed via CCM that all consents and conditions have been discharged and the red line / as-built drawings show that constructed elements of the railway match the consented designs.
C3 | 003 | Planning and Heritage consent conditions which relate to permanent works fully discharged and complied with? | Julie Davis Matthew Carney | Land Use Planning Manager Graduate Engineer | 0207 126 3951 (Internal: 63951) 0207 126 3847 (Internal: 63847) | JulieDavis@crossrail.tfl.gov.uk MatthewCarney@crossrail.tfl.gov.uk | Question initialled by Julie Davis (JulieDavis@crossrail.tfl.gov.uk) once evidence of compliance with consent conditions is received.
C3 | 004 | All Highway consents which may be required either for later contracts or operation transferred to relevant contractor/Crossrail? | Ben Whitton | Traffic Engineer | 0207 126 3993 (Internal: 63993) | Question initialled by Ben Whitton (BenWhitton@crossrail.tfl.gov.uk) and final sign off by Rob Paris. | Question initialled by Ben Whitton (BenWhitton@crossrail.tfl.gov.uk) and final sign off by Rob Paris.
C3 | 005 | All Temporary Highway consents closed out with all traffic management removed and highway reinstated to to Highway Authority satisfaction? | Ben Whitton | Traffic Engineer | 0207 126 3993 (Internal: 63993) | Question initialled by Ben Whitton (BenWhitton@crossrail.tfl.gov.uk) and final sign off by Rob Paris. | Question initialled by Ben Whitton (BenWhitton@crossrail.tfl.gov.uk) and final sign off by Rob Paris.
C4 | ITEM NO. | C4: ENVIRONMENT | Rob Paris | Head of Sustainability & Consents | 0207 126 3943 (Internal: 63943) | robparis@crossrail.tfl.gov.uk | Rob Paris signs the form once all items have been signed off by each relevant Functional Lead
C4 | 001 | All environmental reporting data received (KPIs, recycled content, dust/air quality, noise, water, objectives and targets, carbon footprint/energy model)? | Lorna Mellings | Environment Advisor | T: 020 3054 8440 (ext 88440) | Mellings Lorna <LornaMellings@crossrail.tfl.gov.uk> | Question initialled by Lorna Mellings and final sign off by Rob Paris.
C4 | 002 | Site Waste Management Plan completed and signed off? | Lorna Mellings | Environment Advisor | T: 020 3054 8440 (ext 88440) | Mellings Lorna <LornaMellings@crossrail.tfl.gov.uk> | Question initialled by Lorna Mellings and final sign off by Rob Paris.
C4 | 003 | Survey information handed over (contaminated land, ecology)? | Lorna Mellings | Environment Advisor | T: 020 3054 8440 (ext 88440) | Mellings Lorna <LornaMellings@crossrail.tfl.gov.uk> | Question initialled by Lorna Mellings and final sign off by Rob Paris.
C4 | 004 | Contaminated land verification report accepted? | Lorna Mellings | Environment Advisor | T: 020 3054 8440 (ext 88440) | Mellings Lorna <LornaMellings@crossrail.tfl.gov.uk> | Question initialled by Lorna Mellings and final sign off by Rob Paris.
C4 | 005 | Maintenance regime for site (including landscaping, knotweed management) agreed and signed off? | Lorna Mellings | Environment Advisor | T: 020 3054 8440 (ext 88440) | Mellings Lorna <LornaMellings@crossrail.tfl.gov.uk> | Question initialled by Lorna Mellings and final sign off by Rob Paris.
C4 | 006 | All CARs, NCRs, incident investigations closed out? | Lorna Mellings | Environment Advisor | T: 020 3054 8440 (ext 88440) | Mellings Lorna <LornaMellings@crossrail.tfl.gov.uk> | Question initialled by Lorna Mellings and final sign off by Rob Paris.
C4 | 007 | Environmental design checklists for works complete? | Lorna Mellings | Environment Advisor | T: 020 3054 8440 (ext 88440) | Mellings Lorna <LornaMellings@crossrail.tfl.gov.uk> | Question initialled by Lorna Mellings and final sign off by Rob Paris.
C4 | 008 | Archaeological archive information received (archaeological works only)? | Lorna Mellings | Environment Advisor | T: 020 3054 8440 (ext 88440) | Mellings Lorna <LornaMellings@crossrail.tfl.gov.uk> | Question initialled by Lorna Mellings and final sign off by Rob Paris.
C4 | 009 | Have boreholes been decommissioned in accordance with EA guidance or have records of retained boreholes been passed to the landowner where it has been agreed they will be left as permanent monitoring locations? | Lorna Mellings | Environment Advisor | T: 020 3054 8440 (ext 88440) | Mellings Lorna <LornaMellings@crossrail.tfl.gov.uk> | Question initialled by Lorna Mellings and final sign off by Rob Paris.
C4 | 010 | CEEQUAL assessment completed and submitted or BREEAM assessment completed and submitted? | Lorna Mellings | Environment Advisor | T: 020 3054 8440 (ext 88440) | Mellings Lorna <LornaMellings@crossrail.tfl.gov.uk> | Question initialled by Lorna Mellings and final sign off by Rob Paris.
C4 | 011 | Have post construction actions associated with BREEAM/CEEQUAL been clearly communicated to/documentation been made available to the operator, e.g. requirements for seasonal commissioning, Building User Guide? | Lorna Mellings | Environment Advisor | T: 020 3054 8440 (ext 88440) | Mellings Lorna <LornaMellings@crossrail.tfl.gov.uk> | Question initialled by Lorna Mellings and final sign off by Rob Paris.
C4 | 012 | Environment Agency has confirmed that the works approved under Schedule 17 Part 3 have been completed in accordance with any relevant consent requirements and has confirmed that the consent can be closed out? | Lorna Mellings | Environment Advisor | T: 020 3054 8440 (ext 88440) | Mellings Lorna <LornaMellings@crossrail.tfl.gov.uk> | Question initialled by Lorna Mellings and final sign off by Rob Paris.
C4 | 013 | British Waterways Board (now Canal & River Trust) has confirmed that the works which were approved under Schedule 17 Part5 have been completed in accordance with any relevant consent requirements, and has confirmed that the consent can be closed out? | Lorna Mellings | Environment Advisor | T: 020 3054 8440 (ext 88440) | Mellings Lorna <LornaMellings@crossrail.tfl.gov.uk> | Question initialled by Lorna Mellings and final sign off by Rob Paris.
C4 | 014 | Port of London Authority has confirmed that the works approved under Schedule 17 Part 6 have been completed in accordance with any relevant consent requirements, and has confirmed that the consent can be closed out? | Lorna Mellings | Environment Advisor | T: 020 3054 8440 (ext 88440) | Mellings Lorna <LornaMellings@crossrail.tfl.gov.uk> | Question initialled by Lorna Mellings and final sign off by Rob Paris.
C4 | 015 | All discharge consents & environmental permits which may be required either for later contracts or operation transferred to relevant contractor/Crossrail? | Lorna Mellings | Environment Advisor | T: 020 3054 8440 (ext 88440) | Mellings Lorna <LornaMellings@crossrail.tfl.gov.uk> | Question initialled by Lorna Mellings and final sign off by Rob Paris.
C5 | ITEM NO. | C5: UNDERTAKINGS & ASSURANCES | Rob Paris | Head of Sustainability & Consents | 0207 126 3943 (Internal: 63943) | robparis@crossrail.tfl.gov.uk | Rob Paris signs the form once all items have been signed off by Olabowale Ogunsanya
C5 | 001 | Have all applicable U&As been discharged or handed over in accordance with the accepted Commitments Compliance Plan? | Rob Paris | Head of Sustainability & Consents | - | robparis@crossrail.tfl.gov.uk | Question initialled by Rob Paris when all commitments on the Commitments Tracker have been closed.
C5 | 002 | Has all commitments compliance evidence uploaded into CDT? | Rob Paris | Head of Sustainability & Consents | - | robparis@crossrail.tfl.gov.uk | Question initialled by Rob Paris when all commitments on the Commitments Tracker have been closed.
C6 | ITEM NO. | C6: ESTATES | Paul Bolton - | Head of Estates Land ＆ Property | 0207 126 1997 (Internal: 61997) | PaulBolton@crossrail.tfl.gov.uk | Individual items signed by James Chatfield . Form signed by Paul Bolton when all items are signed off
C6 | 001 | All site/work areas under the custodianship of the contractor have been handed back to the satisfaction of the receiving party and documented on a handback certificate in accordance with the CRL Estates procedure. | James Chatfield | Land and Estates Asset Manager |  | JamesChatfield@crossrail.tfl.gov.uk | Question initialled by James Chatfield and final sign off by Paul Bolton
C7 | ITEM NO. | C7: RAIL INTERFACES | Project Manager or Care & Custody Manager | Project Manager or Care & Custody Manager | - | - | Individual items signed by the site representative who manages the relationship with the third party IM. Once all applicable items have been finalised, the Project Manager or Care & Custody Manager signs the form.
C7 | 001 | Has the Site Rep obtained confirmation that the relevant LU Infrastructure Manager is satisfied that the necessary Assurances have been provided in relation to this contract? | (Insert name) | Site Representative dealing with the LU interface | - | - | Item signed by Site Representative dealing with 3rd Party. Final Sign off by the Project Manager or Care & Custody Manager
C7 | 001 | Has the Site Rep obtained confirmation that the relevant Network Rail Infrastructure Manager is satisfied that the necessary Assurances have been provided in relation to this contract? | (Insert name) | Site Representative dealing with the NR interface | - | - | Item signed by Site Representative dealing with 3rd Party. Final Sign off by the Project Manager or Care & Custody Manager
C7 | 001 | Has the Site Rep obtained confirmation that the relevant DLR Infrastructure Manager is satisfied that the necessary Assurances have been provided in relation to this contract? | (Insert name) | Site Representative dealing with the DLR interface | - | - | Item signed by Site Representative dealing with 3rd Party. Final Sign off by the Project Manager or Care & Custody Manager
C7 | 001 | Has the Site Rep obtained confirmation that the relevant London Overground Infrastructure Manager is satisfied that the necessary Assurances have been provided in relation to this contract? | (Insert name) | Site Representative dealing with the LO interface | - | - | Item signed by Site Representative dealing with 3rd Party. Final Sign off by the Project Manager or Care & Custody Manager
C7 | 002 | Has the Site Rep obtained confirmation that LU 3rd Party Infrastructure Manager got any issues that would indicate that these works cannot be successfully integrated to deliver the completed railway been either resolved or identified for resolution? | (Insert name) | Site Representative dealing with the LU interface | - | - | Item signed by Site Representative dealing with 3rd Party. Final Sign off by the Project Manager or Care & Custody Manager
C7 | 002 | Has the Site Rep obtained confirmation that Network Rail 3rd Party Infrastructure Manager got any issues that would indicate that these works cannot be successfully integrated to deliver the completed railway been either resolved or identified for resolution? | (Insert name) | Site Representative dealing with the NR interface | - | - | Item signed by Site Representative dealing with 3rd Party. Final Sign off by the Project Manager or Care & Custody Manager
C7 | 002 | Has the Site Rep obtained confirmation that DLR 3rd Party Infrastructure Manager got any issues that would indicate that these works cannot be successfully integrated to deliver the completed railway been either resolved or identified for resolution? | (Insert name) | Site Representative dealing with the DLR interface | - | - | Item signed by Site Representative dealing with 3rd Party. Final Sign off by the Project Manager or Care & Custody Manager
C7 | 002 | Has the Site Rep obtained confirmation that London Overground 3rd Party Infrastructure Manager got any issues that would indicate that these works cannot be successfully integrated to deliver the completed railway been either resolved or identified for resolution? | (Insert name) | Site Representative dealing with the LO interface | - | - | Item signed by Site Representative dealing with 3rd Party. Final Sign off by the Project Manager or Care & Custody Manager
C8 | ITEM NO. | C8: SYSTEMWIDE | N/A | N/A | N/A | N/A | N/A
C8 | 1 | Has the Contractor provided records / As Built drawings / Red-line drawings for interfaces with Systemwide and have these documents been through an acceptance review where required? | N/A | N/A | N/A | N/A | N/A - Please refer the procedure Employer's Completion Process CRL1-XRL-O4-GPD-CR001-50018 Rev 8.0.
C8 | 2 | Has the Contractor provided acceptable as built surveys and setting out data (i.e. control points) where required? | N/A | N/A | N/A | N/A | N/A - Please refer the procedure Employer's Completion Process CRL1-XRL-O4-GPD-CR001-50018 Rev 8.0.
C8 | 3 | Has the Contractor provided acceptable Health & Safety Files in cases where that Contractor's civil structure is being taken over by Systemwide for fit-out activities? Files to include records and arrangements of all temporary facilities left in place. | N/A | N/A | N/A | N/A | N/A - Please refer the procedure Employer's Completion Process CRL1-XRL-O4-GPD-CR001-50018 Rev 8.0.
C9 | ITEM NO. | C9: TECHNICAL INFORMATION | (Chris Binns) - Chief Engineer / (TBC) Head of Technical Information | Chief Engineer / Head of Technical Information | Chris Binns | Chris Binns | Chris Binns signs off C9 form after all items have been closed and signed off by the individual item owners
C9 | 001 | Is the CMDL complete and Code 1, with all deliverables at either Code 1 or 4? • Code 1 or 4 approved for current revision • DDx (ProjectWise drawings) C rev plus “As Built” suitability status • DWG (non-ProjectWise drawings, identified as As-Built or Red Line required) Code 1 or 4 | Varsha Ruchaya | Document Control and Data Compliance Manager | T 020 7126 4373 auto 64373 | VarshaRuchaya@crossrail.tfl.gov.uk | Question initialled by Varsha Ruchaya and final sign off by Chris Binns.
C9 | 002 | Are there any Obsolete/Cancelled Crossrail deliverables required to be re-instated? If so, have these all been submitted and accepted formally?’ | Varsha Ruchaya | Document Control and Data Compliance Manager | T 020 7126 4373 auto 64373 | VarshaRuchaya@crossrail.tfl.gov.uk | Question initialled by Varsha Ruchaya and final sign off by Chris Binns.
C9 | 003 | With respect to the WCCC, are the outstanding works / defects, including the outstanding deliverables (if any), listed on the COWL, with unique Punchwork numbers? Is the COWL which is to be listed on the WCCC up to date, accepted and coded Code 1? | Varsha Ruchaya | Document Control and Data Compliance Manager | T 020 7126 4373 auto 64373 | VarshaRuchaya@crossrail.tfl.gov.uk | Question initialled by Varsha Ruchaya and final sign off by Chris Binns.
C9 | 004 | Has the Asset Data provided by the Contractor been Accepted by the IM without comments, with all PWKs, NCRs, FCDs and Observation Reports closed out? | Mark Houghton | Asset Information Provision Manager | T 0207 126 3468 (Auto 63468) | MarkHoughton@crossrail.tfl.gov.uk | Question initialled by Mark Houghton and final sign off by Chris Binns.
C9 | 005 | Is the As Built 3D Master Model and associated 3D Model Issues Report accepted as code 1? | Mark Coleman | Head of CAD Delivery and Support | 0207 126 4387 (Internal: 64387) | MarkColeman@crossrail.tfl.gov.uk | Question initialled by Mark Coleman and final sign off by Chris Binns.
C9 | 006 | Are all As Built drawings accepted as code 1? | Mark Coleman | Head of CAD Delivery and Support | 0207 126 4387 (Internal: 64387) | MarkColeman@crossrail.tfl.gov.uk | Question initialled by Mark Coleman and final sign off by Chris Binns.
C9 | 007 | Is the design in accordance with CRL CAD standards and CAD related requirements within the Works Information? | Mark Coleman | Head of CAD Delivery and Support | 0207 126 4387 (Internal: 64387) | MarkColeman@crossrail.tfl.gov.uk | Question initialled by Mark Coleman and final sign off by Chris Binns.
C9 | 008 | Have all the O&M Deliverables and Manuals been submitted by the Contractor, accepted by the Supervisor’s Rep (PFE) and are they in compliance with CRL requirements? | Patrick Barry | Handover Manager – Central Section Patrick Barry | 0207 126 3523 (Internal: 63523) | Barry Patrick <PatrickBarry@crossrail.tfl.gov.uk> | Question initialled by Patrick Barry and final sign off by Chris Binns.
C9 | 009 | Is all O&M deliverable information available to enable CRL to add all O&M deliverables to the Operational and Maintenance structure on eB and link them to the O&M manuals? | Patrick Barry | Handover Manager – Central Section Patrick Barry | 0207 126 3523 (Internal: 63523) | Barry Patrick <PatrickBarry@crossrail.tfl.gov.uk> | Question initialled by Patrick Barry and final sign off by Chris Binns.
C10 | ITEM NO. | C10: Third Party Agreements | Richard Ellis - Head of Agreement Management | Head of Agreement Management | 0207 126 2863 (Internal: 62863) | RichardEllis@crossrail.tfl.gov.uk | Richard Ellis signs off C10 form after all agreements have been closed on the agreements tracker and/or responsibility for managing the agreement has been transferred to a new agreement manager. signed off by
C10 | 001 | All Third Party Agreements (TPA) that relate to this Contract have been identified by reference to the Agreements Management System and there are no outstanding duties or obligations which would prevent finalisation of the closure process as it relates to the Contract. | Esme Hobbs | Agreements Manager | 0207 126 2875 (Internal: 62875) | EsmeHobbs@crossrail.tfl.gov.uk | Question initialled by Esme Hobbs or Simon Pope and final sign off by Richard Ellis.
C10 | 002 | Where TPA obligations have been incorporated into the Contract work scope these have been reviewed and deemed discharged. It is to be noted that the majority of TPA obligations are not discharged via the delivery Contracts and are subject to a separate Agreement Close Out and Handover process. | Esme Hobbs | Agreements Manager | 0207 126 2875 (Internal: 62875) | EsmeHobbs@crossrail.tfl.gov.uk | Question initialled by Esme Hobbs or Simon Pope and final sign off by Richard Ellis.
C10 | 003 | Any outstanding TPA obligations that are related to the Element or Elements associated with this Contract are being managed outside of ECP and within the Agreement Close Out and Handover process. | Esme Hobbs | Agreements Manager | 0207 126 2875 (Internal: 62875) | EsmeHobbs@crossrail.tfl.gov.uk | Question initialled by Esme Hobbs or Simon Pope and final sign off by Richard Ellis.
C20 | ITEM NO. | C20: Completion | Piotr Swieboda | Completion Manager | 0207 126 4039 (Internal: 64039) 07926 100380 | PiotrSwieboda@crossrail.tfl.gov.uk | Completion Manager signs the form after all items have been signed off by the Supervisor's Rep, the PM and the FE Manager.
C20 | 001 | Have all CARs, NCRs FCDs & RFIs been properly closed out in the system? | Supervisor's Rep (PFE) (Insert name) | - | - | - | Question initialled by Supervisor’s Rep and final sign off by Completion Manager Piotr Swieboda
C20 | 002 | Has the C-ICD document or Handover Plan been submitted by the Contractor and accepted by CRL | Supervisor's Rep (PFE) (Insert name) | - | - | - | Question initialled by Supervisor’s Rep and final sign off by Completion Manager Piotr Swieboda
C20 | 003 | Have all packages been completed and Construction Certificates signed off? | Certification Manager | Judith Griffiths | 07411009264 | JudithGriffiths@crossrail.tfl.gov.uk | Question initialled by Lead Certification Manager and final sign off by Completion Manager Piotr Swieboda
C20 | 004 | Has all work scope removed from the current contract been formally transferred to the follow-on contract? Or alternatively has all work scope removed from the current contract been formally accepted by the end user for instances where there is no follow-on contract? Note: List of items de-scoped and transferred/accepted to be attached as evidence. | Project Manager (Insert name) | - | - | Question initialled by Project Manager | Question initialled by Project Manager
C20 | 005 | Does the Contractor have a Care and Maintenance Plan which has been reviewed by CEG and accepted by the CRL Project Manager? | Project Manager (Insert name) | - | - | Signed by CRL project manager | Signed by CRL Project manager
C20 | 006 | Has the CRL Project Manager agreed/clarified all handover matters with the Care and Maintenance Manager? | Project Manager (Insert name) | - | - | Singed by CRL PM and the Care Maintenance Manager. | Singed by CRL PM and the Care Maintenance Manager.
C20 | 007 | Has provision been made for Supervisor’s cover during the Defects Liability Period ? | Piotr Swieboda | Completion Manager | 0207 126 4039 (Internal: 64039) 07926 100380 | PiotrSwieboda@crossrail.tfl.gov.uk | Question initialled by Completion Manager
C20 | 008 | Have all the interfaces with utility providers been closed out? | Mark McColgan MarkMcColgan@crossrail.tfl.gov.uk | ADM Project Manager / Utilities Project Manager | - | Question initialled by ADM Project Manager / Utilities Project Manager (Mark McColgan) + Sign-off by Supervisor's Rep. | Question initialled by ADM Project Manager / Utilities Project Manager (Mark McColgan) + Sign-off by Supervisor's Rep.
C20 | 009 | Has the contractor delivered all training in accordance with the agreed Training Strategy and Plan? | Stuart Wilkinson | CRL Training Manager | 0203 054 8372 (Internal: 88372 | Stuart Wilkinson <StuartWilkinson@crossrail.tfl.gov.uk> CRL Training Manager | Signed by CRL Training Manager
C30 | ITEM NO. | C30: Authorisation to Accept WCCC | Piotr Swieboda | Completion Manager | 0207 126 4039 (Internal: 64039) 07926 100380 | PiotrSwieboda@crossrail.tfl.gov.uk | Signed by the Completion Manager when all forms have been signed by the Function Lead.
C30 | 1 | I confirm that the Employer’s Completion Process for Contract CXXX has been completed to my satisfaction and the Whole Contract Construction Certificate/ Sectional Contract Construction Certificate can be accepted. | Piotr Swieboda | Completion Manager | 0207 126 4039 (Internal: 64039) 07926 100380 | PiotrSwieboda@crossrail.tfl.gov.uk | Sign off by the Completion Manager (Piotr Swieboda) or the Supervisor (TBC).
Note on F2: v_JohnsonMonteiro: Phone numbers might have changed due to Office move etc.

## Sheet1 (hidden)
Open
Closed
Not Applicable
Closed for ECP1
Tracker template rev | 4.1